## Overview
Overview | Meeting Log | Meeting Report | Lists & Config
HBX Commissioning Review - Overview
Open this before a meeting: pick the meeting date below and everything updates automatically from Meeting Log.
Current Meeting Date: | 2026-10-01
3 |  |  | 3 |  |  | 1 | 0 | 2 | 1
Total Subjects |  |  | Open Actions |  |  | Overdue Actions | Closed | Carried Over from Previous Meeting | New Topics This Meeting
Attendees
Meeting Date | Meeting Type | Attendees
2026-10-01 | Monthly | Person A, Person B, Contractor A representative
1. FOLLOW-UP FROM PREVIOUS MEETING (open, not yet touched today)
Subject | Sub-topic | Discussion | Action | Owner | Due Date | Status
Documentation | Documentation | Document A cannot be validated - missing the calibration certificate. | J. Smith to retrieve the missing certificate. | J. Smith | 0 | Open
Safety | Design / Engineering | SSOW draft submitted for review. | R. Taylor to review and approve the SSOW. | R. Taylor | 2026-09-20 | Open
2. NEW TOPICS (raised today)
Subject | Sub-topic | Discussion | Action | Owner | Due Date | Status
Testing / Results | Testing | First functional test results reviewed. | A. Brown to issue the test report. | A. Brown | 2026-10-20 | Open
To continue a topic above: add a new row in Meeting Log with the SAME Subject/Sub-topic (pick from the dropdown) and today's date. Sort Meeting Log by Subject any time to see a topic's full history together.
3. ACTIONS TO FOLLOW (all currently open topics)
Subject | Action | Owner | Due Date | Status | Priority
Documentation | J. Smith to chase the supplier. | J. Smith | 0 | In Progress | Medium
Safety | R. Taylor to review and approve the SSOW. | R. Taylor | 2026-09-20 | Open | High
Testing / Results | A. Brown to issue the test report. | A. Brown | 2026-10-20 | Open | High
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically

## Meeting Log
Overview | Meeting Log | Meeting Report | Lists & Config
Meeting Log
The single database. One row per subject discussed at one meeting - never overwritten, never deleted. To see a topic's full history, sort by Subject (click the column header's sort button): every past entry for that topic groups together on screen, no other sheet needed.
Subject | Sub-topic | Meeting Date | Discussion / Notes | Agreed Action | Owner | Due Date | Status | Priority | Topic Key | Overdue?
Documentation | Documentation | 2026-09-01 | Document A cannot be validated - missing the calibration certificate. | J. Smith to retrieve the missing certificate. | J. Smith |  | Open | Medium | Documentation¦Documentation | No
Documentation | Documentation | 2026-10-01 | Still waiting on the calibration certificate from the supplier. | J. Smith to chase the supplier. | J. Smith |  | In Progress | Medium | Documentation¦Documentation | No
Safety | Design / Engineering | 2026-09-01 | SSOW draft submitted for review. | R. Taylor to review and approve the SSOW. | R. Taylor | 2026-09-20 | Open | High | Safety¦Design / Engineering | Yes
Testing / Results | Testing | 2026-10-01 | First functional test results reviewed. | A. Brown to issue the test report. | A. Brown | 2026-10-20 | Open | High | Testing / Results¦Testing | No
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically
Formulas:
Overdue? = IF([Overview]="","",IF(AND([Status]<>"Closed",[Status]<>"Cancelled",[Due Date]<>"",[Due Date]<TODAY()),"Yes","No"))

## Meeting Report
Overview | Meeting Log | Meeting Report | Lists & Config
Meeting Report
Mirrors the meeting date selected on Overview - change it there to generate a report for a different meeting. Short enough to copy straight into minutes or an email.
Meeting Date: | 2026-10-01 |  | Meeting Type: | Monthly
Attendees: | Person A, Person B, Contractor A representative
1. FOLLOW-UP FROM PREVIOUS MEETING
Subject | Sub-topic | Discussion | Action | Owner | Status
Documentation | Documentation | Document A cannot be validated - missing the calibration certificate. | J. Smith to retrieve the missing certificate. | J. Smith | Open
Safety | Design / Engineering | SSOW draft submitted for review. | R. Taylor to review and approve the SSOW. | R. Taylor | Open
2. NEW TOPICS
Subject | Sub-topic | Discussion / Notes | Agreed Action | Owner | Due Date | Status
Testing / Results | Testing | First functional test results reviewed. | A. Brown to issue the test report. | A. Brown | 2026-10-20 | Open
3. DISCUSSION LOG FOR THIS MEETING
Subject | Sub-topic | Discussion / Notes | Agreed Action | Owner
Documentation | Documentation | Still waiting on the calibration certificate from the supplier. | J. Smith to chase the supplier. | J. Smith
Testing / Results | Testing | First functional test results reviewed. | A. Brown to issue the test report. | A. Brown
4. OPEN / OVERDUE ACTIONS
Subject | Action | Owner | Due Date | Status
Safety | R. Taylor to review and approve the SSOW. | R. Taylor | 2026-09-20 | Open
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically

## Lists & Config
Overview | Meeting Log | Meeting Report | Lists & Config
Lists & Config
Dropdown values used across the workbook. Add or remove values here - every dropdown updates automatically. No formulas here need to change.
Subject | Sub-topic | Status | Priority | Meeting Type
Commissioning Planning | Planning | Open | Low | Weekly
Site / Field Activities | Progress | In Progress | Medium | Monthly
Documentation | Preparation | Closed | High | Ad hoc
Testing / Results | Execution | On Hold | Critical
Interfaces | Testing | Cancelled
Engineering | Punch List
Quality | Documentation
Safety | NCR / Quality
Resources / Manpower | Design / Engineering
Schedule | Interface
Other | Resource
Schedule
Risk / Issue
Decision
Other
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically