## DASHBOARD
COMMISSIONING DASHBOARD
CONTRACT STATUS
Worst item
Share late
Earliest commissioning start
Core deliverables missing
Data quality flags
PROGRESS
| Done | In progress | Late | Inactive | Missing | Total | % done
DOCUMENTS
ACTIONS
Kind | Subject | Scope | Owner | Target date | Days late
Level | Deliverable | Where | Needed by
Kind | Subject | Scope | Owner | Target date | Days left
4. BY SYSTEM
System | System name | Equip. | Docs | Done | Late | At risk | Core missing | % done | Status
5. EQUIPMENT TO WATCH most severe first
System | Equipment | Docs | Done | Late | Core missing | % done | Status
6. MILESTONES
Milestone | Note | Planned date | Actual date | Days from today
CHARTS

## TRACKER
DELIVERABLES TRACKER
One row per document per thing it covers: the whole contract (Scope = All), a system, or a piece of equipment. A document covering three systems is three rows. Fill Actual start when work begins. Days late: positive = late, negative = float.
Type | Scope | System | Equipment | Document no. | Teamcenter no. | Rev. | Responsible (drafting) | Approver | Status | Actual start | Target override | Target approval | Source | Actual approval | Days late | State | Check | Comment | Scope date | Auto target | Active | Done | Inactive | Phase | k late | k wip | k coming
Commissioning Procedure | Equipment | SYS-01 | EQ-001 Example equipment item | DMIC-SYS-01-CPR-001 | TC-6100001 | A | B. Example | C. Example | W1 - Draft | [8 empty] | EXAMPLE ROW - overwrite with your first deliverable
Formulas:
Days late = IF([Active]=0,"",IF([Done]=1,IF([Actual approval]="","",[Actual approval]-[Target approval]),IF([Target approval]="","",TODAY()-[Target approval])))
Note on F3: Teamcenter identifier of the document. Kept separate from the contract document number so either can be searched on its own.
Note on G3: Revision of the document as it stands today - A, B, 01, 02, whatever your numbering uses. Kept in its own column so the number never has to be retyped when the revision moves on.
Note on L3: Type a date here only when the automatic calculation cannot know something - a cross-system dependency, a site event. The Source column then reads Manual. Clear this cell to fall back to the automatic date.
Note on M3: Automatic = the commissioning start of whatever this row covers (actual start if one is filled in on SETUP, otherwise the planned start), minus the lead time of the type. Post-commissioning types are measured back from their anchor milestone instead. Blank means no start date is set for what this row covers.

## ACTIONS
ACTIONS
One filterable table. Link an action to a system, an equipment item, a document, any combination, or nothing at all - every link is optional.
Action ID | Description | Phase | System | Equipment | Document no. | Owner | Actual start | Due date | Done date | Status | Days late | State | Comment | k late | k wip | k coming
ACT-001 | EXAMPLE - overwrite with your first action | Pre-commissioning | SYS-01 |  |  | B. Example |  | 2026-09-08 |  | Open
Formulas:
Days late = IF([Action ID]="","",IF([Status]=A_DONE,IF([Done date]="","",[Done date]-[Due date]),IF([Due date]="","",TODAY()-[Due date])))

## SETUP
SETUP - CONTROL PANEL
Everything in the workbook is driven from this sheet. Blue cells are yours to edit; grey cells calculate themselves. To drop a status code, a milestone or a document type, CLEAR the cells - never delete the row: the rest of the workbook is addressed by row and deleting one breaks it.
1 - CONTRACT
Contract number
Contract name
Contract Manager
Commissioning Manager
Quality Lead
2 - THRESHOLDS
Document alert window (days) | 30 | An unapproved document turns At risk inside this many days before its target.
Action alert window (days) | 3 | Same idea, for actions.
Coming horizon (days) | 90 | How far ahead the COMING block looks.
Earliest commissioning start (calculated) |  | Drives the milestone dates in section 5.
3 - WORDING rename anything here: the whole workbook follows
Document approved (S4A reached) or published | Done
Target approval date passed without approval | Late
Actual start filled in, not late | In progress
Due inside the document alert window | At risk
Due inside the coming horizon, not started | Coming
Due beyond the horizon | Not yet due
Cancelled, revoked, superseded, transferred, destroyed | Inactive
Actions only: due beyond the action alert window | On track
No commissioning start date behind this row | Scope not resolved
Anchor milestone has no date | No target date
Type missing from the library | Type not configured
Actions only: due date not filled in | No due date
3b - CONTRACT STATUS WORDING
At least one document or action is late | DELAYED
Nothing late, but something is at risk or missing | AT RISK OF DELAY
Nothing late, nothing at risk | ON SCHEDULE
3c - ACTION STATUS WORDING
Action status 1 | Open
Action status 2 | In progress
Action status 3 | On hold
Action status 4 | Done
4 - DOCUMENT STATUS CODES 'Counts as' is how each code is read everywhere else
Status code | Family | Counts as
W0 - Work In Progress | Preparation | In progress
W1 - Draft | Preparation | In progress
W2 - Revoked | Preparation | Inactive
S2 - For Information | Review | In progress
S3 - For Review | Review | In progress
S4 - For Internal Approval | Review | In progress
S4A - Approved | Approval result | Done
S4B - Comments | Approval result | In progress
S4C - Rejected | Approval result | In progress
S6 - For Acceptance | Acceptance | In progress
S6Q - Quality Checked | Acceptance | In progress
S6B - Comments | Acceptance | In progress
S6C - Rejected | Acceptance | In progress
P1 - For Implementation | Published | Done
P2 - For Costing | Published | Done
P3 - For Tender | Published | Done
P4 - For Contractor Design | Published | Done
P5 - For Manufacture / Procurement | Published | Done
P6 - For Construction | Published | Done
P7 - As-Built | Published | Done
A1 - Cancelled | Closed | Inactive
A2 - Superseded | Closed | Inactive
A3 - Transferred | Closed | Inactive
A4 - Destroyed | Closed | Inactive
S4A and the P-codes stop the delay counter. A-codes and W2 are Inactive: they leave every active counter, stay visible in their own column, and no longer count as coverage for a required deliverable.
5 - MILESTONES dates only; anything to organise goes in ACTIONS
Milestone | Offset from earliest start (days) | Date typed (optional) | Planned date | Actual date | Note
Kick Off Meeting | -360
Commissioning Readiness Review | -60
Authority To Start | -14
NTP | -7
Commissioning Start | 0
Commissioning Finish | 180
Functional Takeover | 195
Beneficial Use | 205
Maintenance Transfer | 220
Temporary Operations Transfer | 235
Final Takeover | 250
6 - SYSTEMS
System ID | System name | Commissioning Engineer | Earliest equipment start | Equip. | Docs | Done | Late | At risk | Core missing | % done | Status
SYS-01 | EXAMPLE - overwrite with your first system | B. Example
7 - EQUIPMENT the planned commissioning start typed here drives every target date behind that equipment
Parent system | Equipment | Planned comm. start | Planned comm. finish | Actual start | Actual finish | Docs | Done | Late | Core missing | % done | Status | Key | Start used
SYS-01 | EQ-001 Example equipment item | 2027-04-22 | 2027-06-06
8 - DOCUMENT TYPE LIBRARY
Document type | Phase | Core required (ATS) | Anchor milestone | Lead before anchor (days) | Default scope | Note | Core key
Basis of Commissioning | Pre-commissioning | Yes | Commissioning Start | 360 | All | T-12 months
Surveillance Strategy | Pre-commissioning | Yes | Commissioning Start | 360 | All | T-12 months, ATS
Surveillance Programme | Pre-commissioning | Yes | Commissioning Start | 270 | System | T-9 months, ATS
Competency Evidence | Pre-commissioning | Yes | Commissioning Start | 270 | All | T-9 months, ATS
Safe System Of Work | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS
Risk Assessment And Method Statement | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS
System Commissioning Programme | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS
Commissioning Procedure | Pre-commissioning | Yes | Commissioning Start | 90 | Equipment | T-3 months, ATS
Inspection and Test Plan | Pre-commissioning | Yes | Commissioning Start | 90 | Equipment | T-3 months, ATS
Initial End Of Erection Status Report | Pre-commissioning | No | Commissioning Start | 90 | Equipment | T-3 months
Planned End Of Erection Status Report | Pre-commissioning | Yes | Commissioning Start | 30 | Equipment | T-1 month, ATS
Authority To Start Evidence | Pre-commissioning | Yes | Commissioning Start | 14 | System | T-2 weeks, ATS
Commissioning Results Sheet | Commissioning | No | Commissioning Finish | 0 | Equipment | During commissioning
Commissioning Phase Report | Post-commissioning | No | Functional Takeover | 15 | System | Anchor estimated
Handover Certificate | Post-commissioning | No | Functional Takeover | 0 | Equipment | Anchor estimated
Functional Takeover Package | Post-commissioning | No | Functional Takeover | 15 | System | Before FTC
Care And Maintenance Plan | Post-commissioning | No | Maintenance Transfer | 30 | System | Not in the spec lead table
Maintenance Transfer Package | Post-commissioning | No | Maintenance Transfer | 15 | System | Before TFM
Temporary Operations Transfer Package | Post-commissioning | No | Temporary Operations Transfer | 15 | System | Before TFTO
Final End Of Erection Status Report | Post-commissioning | No | Final Takeover | 15 | System | Before Final Takeover
Months are converted at 30 days each (T-3 months = 90), which reproduces the worked example in the source specification exactly. Post-commissioning types are anchored to a named milestone rather than to a guessed number of days.
9 - PHASES
Phase | Order
Pre-commissioning | 1
Commissioning | 2
Post-commissioning | 3
10 - PEOPLE feeds the Responsible, Approver and Owner dropdowns
Name | Role
A. Example | Commissioning Manager
B. Example | Commissioning Engineer
C. Example | Approver
Note on C15: Earliest commissioning start across all equipment in section 7 - the actual start where one is filled in, the planned start otherwise. Every 'Commissioning Start' anchored target date ultimately derives from the start date of whatever the document covers, not from this single figure.
Note on D71: Type a date here to override the offset calculation for that milestone.
Note on K89: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K90: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K91: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K92: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K93: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K94: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K95: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K96: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K97: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K98: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K99: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K100: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K101: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K102: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K103: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K104: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K105: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K106: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K107: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K108: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K109: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K110: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K111: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K112: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K113: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on F116: Fill this in when the equipment actually starts commissioning. From that moment every target date behind this equipment is measured from the actual start instead of the planned one.

## HOW IT WORKS
HOW IT WORKS
This workbook does not measure progress. It measures whether deliverables are on time against the commissioning start of whatever they cover.
THE ONE RULE
Target approval date | The earliest commissioning start among what the document covers (actual if known, otherwise planned), minus the lead time of its type. Post-commissioning types are measured back from their anchor milestone instead.
Days late | Positive = late. Negative = float. One convention everywhere.
Scope | All = the whole contract. System = one system. Equipment = one item. A document covering three systems is three rows.
START HERE
1. Contract and thresholds | SETUP sections 1 and 2.
2. Systems and equipment | SETUP sections 6 and 7. The commissioning start you type against each equipment item is what drives every target date behind it. Fill Actual start when the item really starts: from then on every target behind it is measured from the actual date instead of the planned one, and the hidden 'Start used' column shows which of the two is in force. Equipment with neither date leaves its documents with a blank target and the Check column explains why.
3. Check the type library | SETUP section 8. Phase, anchor milestone, lead time, core (ATS) flag and default scope for each type.
4. Enter deliverables | TRACKER. Pick a Type and a Scope; the target date appears.
5. Work the lists | DASHBOARD. In progress, Missing, Coming - documents and actions together.
READING THE TRACKER
Document no. / Teamcenter no. / Rev. | Three separate columns on purpose. The contract document number and the Teamcenter identifier each stay searchable on their own, and the revision moves on without the number ever being retyped. Filter or sort on any of them.
Target override | Type a date to force a target the calculation cannot know - a cross-system dependency, a site event. The Source column then reads Manual. Clear the cell to fall back to Auto.
Source | Auto = calculated. Manual = you overrode it. Nothing is ever silently overwritten.
Check | Data-quality flag: scope not set, equipment not in that system, approved with no approval date. Empty means the row is clean.
Greyed cells | Not relevant for that row's scope. System is greyed for Scope = All; Equipment is greyed unless Scope = Equipment.
STATE COLOURS
Red | Late - the target approval date has passed.
Amber | At risk - due inside the document alert window.
Blue | In progress - an actual start date is filled in.
Pale amber | Coming - not started, due inside the horizon.
Green | Done - S4A reached, a P-code published, or an approval date entered.
Grey | Inactive - cancelled, revoked, superseded, transferred, destroyed.
Orange | Needs attention: scope not resolved, no target date, type not configured, or a data-quality flag.
WHAT 'MISSING' MEANS
Missing | A deliverable flagged Core required (ATS) in the library that does not exist as a row at all for a system or an equipment item. The workbook builds the expected matrix from the library and reports the gaps, ordered by when each would have been needed.
Covered by | A system-wide or contract-wide document counts as coverage for the equipment beneath it. Inactive documents do not count as coverage.
NEVER DELETE A ROW ON SETUP
Why | The rest of the workbook reads SETUP by position. Deleting a row there - a status code, a milestone, a wording line - destroys the reference and the dashboard lists go blank without saying why. SETUP is therefore protected against inserting and deleting rows and columns. Every blue cell stays editable as normal.
To drop a status code | Clear the cells on that line instead. An empty line is simply ignored everywhere.
If you really must | Review > Unprotect Sheet - there is no password. If a deletion does break something, a red banner appears at the top of the DASHBOARD instead of the lists silently emptying.
CAPACITY AND LIMITS
Rows | TRACKER 500 rows - ACTIONS 150 - systems 25 - equipment 80 - milestones 15 - core types tracked for gaps 12.
One flat table | The TRACKER is a single table, not one block per type. Capacity is shared: 500 rows go wherever they are needed, and you can filter or sort across every type at once.
To add rows | Copy the last data row and paste down, then widen the named ranges in Formulas > Name Manager.
No macros | Formulas only. Nothing to enable, nothing a corporate policy can block.
Excel version | Uses no function newer than Excel 2007, so it runs on any current corporate build.
ASSUMPTIONS
Months to days | 30 days per month (T-3 months = 90), which reproduces the worked example in the source specification exactly.
Post-commissioning anchors | Anchored to named milestones rather than to guessed day counts. Adjust the offsets in SETUP section 5.
Equipment with no date | If nothing behind a row has a commissioning start, the row reads 'Scope not resolved' rather than inventing a target.

## LISTS (hidden)
LISTS - staging. Generated automatically; do not edit.
| Done | All | Yes
| In progress | System | No
| Inactive | Equipment