## DASHBOARD
COMMISSIONING DASHBOARD
Set the contract name in SETUP ¦ what is late, what has never been created, what is coming.
CONTRACT STATUS
AT RISK OF DELAY |  |  | Worst item |  | nothing late
|  |  | Share late |  | 0%
|  |  | Earliest commissioning start |  | 22-Apr-2027 in 240 d
|  |  | Core deliverables missing |  | 10
|  |  | Data quality flags |  | 0
PROGRESS
| Done | In progress | Late | Inactive | Missing | Total | % done
DOCUMENTS | 0 | 0 | 0 | 0 | 10 | 1 | 0%
ACTIONS | 0 | 0 | 0 | 0 | 0 | 1 | 0%
1. IN PROGRESS work started, or already late. Most late first. Showing 0 of 0
Kind | Subject | Scope | Owner | Target date | Days late
2. MISSING core deliverables that do not exist yet. Soonest needed first. Showing 10 of 10
Level | Deliverable | Where | Needed by
Contract | Basis of Commissioning | Whole contract | 2026-04-27 | [6 empty] | 46139
Contract | Surveillance Strategy | Whole contract | 2026-04-27 | [6 empty] | 46139
Contract | Competency Evidence | Whole contract | 2026-07-26 | [6 empty] | 46229
System | Surveillance Programme | SYS-01 | 2026-07-26 | [6 empty] | 46229
System | Safe System Of Work | SYS-01 | 2026-10-24 | [6 empty] | 46319
System | Risk Assessment And Method Statement | SYS-01 | 2026-10-24 | [6 empty] | 46319
System | System Commissioning Programme | SYS-01 | 2026-10-24 | [6 empty] | 46319
Equipment | Inspection and Test Plan | EQ-001 Example equipment item | 2027-01-22 | [6 empty] | 46409.0003
Equipment | Planned End Of Erection Status Report | EQ-001 Example equipment item | 2027-03-23 | [6 empty] | 46469.0003
System | Authority To Start Evidence | SYS-01 | 2027-04-08 | [6 empty] | 46485
3. COMING not started, due inside the horizon set in SETUP. Soonest first. Showing 1 of 1
Kind | Subject | Scope | Owner | Target date | Days left
Action | ACT-001 - EXAMPLE - overwrite with your first action | SYS-01 | B. Example | 2026-09-08 | 14 |  |  |  |  | -14
4. BY SYSTEM
System | System name | Equip. | Docs | Done | Late | At risk | Core missing | % done | Status
SYS-01 | EXAMPLE - overwrite with your first system | 1 | 1 | 0 | 0 | 0 | 5 | 0% | At risk
5. EQUIPMENT TO WATCH most severe first
System | Equipment | Docs | Done | Late | Core missing | % done | Status
SYS-01 | EQ-001 Example equipment item | 1 | 0 | 0 | 2 | 0% | At risk |  |  | 21.0001
6. MILESTONES
Milestone | Note | Planned date | Actual date | Days from today
Kick Off Meeting |  | 2026-04-27 |  | -120
Commissioning Readiness Review |  | 2027-02-21 |  | 180
Authority To Start |  | 2027-04-08 |  | 226
NTP |  | 2027-04-15 |  | 233
Commissioning Start |  | 2027-04-22 |  | 240
Commissioning Finish |  | 2027-10-19 |  | 420
Functional Takeover |  | 2027-11-03 |  | 435
Beneficial Use |  | 2027-11-13 |  | 445
Maintenance Transfer |  | 2027-11-28 |  | 460
Temporary Operations Transfer |  | 2027-12-13 |  | 475
Final Takeover |  | 2027-12-28 |  | 490
CHARTS

## TRACKER
DELIVERABLES TRACKER
One row per document per thing it covers: the whole contract (Scope = All), a system, or a piece of equipment. A document covering three systems is three rows. Fill Actual start when work begins. Days late: positive = late, negative = float.
Type | Scope | System | Equipment | Document no. | Responsible (drafting) | Approver | Status | Actual start | Target override | Target approval | Source | Actual approval | Days late | State | Check | Comment | Scope date | Auto target | Active | Done | Inactive | Phase | k late | k wip | k coming
Commissioning Procedure | Equipment | SYS-01 | EQ-001 Example equipment item | DMIC-SYS-01-CPR-001 | B. Example | C. Example | W1 - Draft |  |  | 2027-01-22 | Auto |  | -150 | Not yet due |  | EXAMPLE ROW - overwrite with your first deliverable | 2027-04-22 | 2027-01-22 | 1 | 0 | 0 | Pre-commissioning
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
Formulas:
Target approval = IF([Type]="","",IF([Target override]<>"",[Target override],[Auto target]))
Days late = IF([Active]=0,"",IF([Done]=1,IF([Actual approval]="","",[Actual approval]-[Target approval]),IF([Target approval]="","",TODAY()-[Target approval])))
Scope date = IF(OR([Type]="",[Scope]=""),"",IF([Scope]="Equipment",IFERROR(INDEX(EQP_START,MATCH([Equipment],EQP_NOM,0)),""),IF([Scope]="System",IFERROR(INDEX(SYS_EARLIEST,MATCH([System],SYS_ID,0)),""),IF([Scope]="All",CTR_EARLIEST,""))))
Note on J3: Type a date here only when the automatic calculation cannot know something - a cross-system dependency, a site event. The Source column then reads Manual. Clear this cell to fall back to the automatic date.
Note on K3: Automatic = the commissioning start of whatever this row covers (actual if known, otherwise planned), minus the lead time of the type. Post-commissioning types are measured back from their anchor milestone instead.

## ACTIONS
ACTIONS
One filterable table. Link an action to a system, an equipment item, a document, any combination, or nothing at all - every link is optional.
Action ID | Description | Phase | System | Equipment | Document no. | Owner | Actual start | Due date | Done date | Status | Days late | State | Comment | k late | k wip | k coming
ACT-001 | EXAMPLE - overwrite with your first action | Pre-commissioning | SYS-01 |  |  | B. Example |  | 2026-09-08 |  | Open | -14 | Coming |  |  |  | -14
Formulas:
Days late = IF([Action ID]="","",IF([Status]=A_DONE,IF([Done date]="","",[Done date]-[Due date]),IF([Due date]="","",TODAY()-[Due date])))

## SETUP
SETUP - CONTROL PANEL
Everything in the workbook is driven from this sheet. Blue cells are yours to edit; grey cells calculate themselves. Nothing else needs rebuilding.
1 - CONTRACT
Contract number
Contract name
Contract Manager
Commissioning Manager
Quality Lead
2 - THRESHOLDS
Document alert window (days) | 30 | An unapproved document turns At risk inside this many days before its target.
Action alert window (days) | 3 | Same idea, for actions.
Coming horizon (days) | 90 | How far ahead the COMING block looks.
Earliest commissioning start (calculated) | 2027-04-22 | Drives the milestone dates in section 5.
3 - WORDING rename anything here: the whole workbook follows
Document approved (S4A reached) or published | Done
Target approval date passed without approval | Late
Actual start filled in, not late | In progress
Due inside the document alert window | At risk
Due inside the coming horizon, not started | Coming
Due beyond the horizon | Not yet due
Cancelled, revoked, superseded, transferred, destroyed | Inactive
Actions only: due beyond the action alert window | On track
No commissioning start date behind this row | Scope not resolved
Anchor milestone has no date | No target date
Type missing from the library | Type not configured
Actions only: due date not filled in | No due date
3b - CONTRACT STATUS WORDING
At least one document or action is late | DELAYED
Nothing late, but something is at risk or missing | AT RISK OF DELAY
Nothing late, nothing at risk | ON SCHEDULE
3c - ACTION STATUS WORDING
Action status 1 | Open
Action status 2 | In progress
Action status 3 | On hold
Action status 4 | Done
4 - DOCUMENT STATUS CODES 'Counts as' is how each code is read everywhere else
Status code | Family | Counts as
W0 - Work In Progress | Preparation | In progress
W1 - Draft | Preparation | In progress
W2 - Revoked | Preparation | Inactive
S2 - For Information | Review | In progress
S3 - For Review | Review | In progress
S4 - For Internal Approval | Review | In progress
S4A - Approved | Approval result | Done
S4B - Comments | Approval result | In progress
S4C - Rejected | Approval result | In progress
S6 - For Acceptance | Acceptance | In progress
S6Q - Quality Checked | Acceptance | In progress
S6B - Comments | Acceptance | In progress
S6C - Rejected | Acceptance | In progress
P1 - For Implementation | Published | Done
P2 - For Costing | Published | Done
P3 - For Tender | Published | Done
P4 - For Contractor Design | Published | Done
P5 - For Manufacture / Procurement | Published | Done
P6 - For Construction | Published | Done
P7 - As-Built | Published | Done
A1 - Cancelled | Closed | Inactive
A2 - Superseded | Closed | Inactive
A3 - Transferred | Closed | Inactive
A4 - Destroyed | Closed | Inactive
S4A and the P-codes stop the delay counter. A-codes and W2 are Inactive: they leave every active counter, stay visible in their own column, and no longer count as coverage for a required deliverable.
5 - MILESTONES dates only; anything to organise goes in ACTIONS
Milestone | Offset from earliest start (days) | Date typed (optional) | Planned date | Actual date | Note
Kick Off Meeting | -360 |  | 2026-04-27
Commissioning Readiness Review | -60 |  | 2027-02-21
Authority To Start | -14 |  | 2027-04-08
NTP | -7 |  | 2027-04-15
Commissioning Start | 0 |  | 2027-04-22
Commissioning Finish | 180 |  | 2027-10-19
Functional Takeover | 195 |  | 2027-11-03
Beneficial Use | 205 |  | 2027-11-13
Maintenance Transfer | 220 |  | 2027-11-28
Temporary Operations Transfer | 235 |  | 2027-12-13
Final Takeover | 250 |  | 2027-12-28
6 - SYSTEMS
System ID | System name | Commissioning Engineer | Earliest equipment start | Equip. | Docs | Done | Late | At risk | Core missing | % done | Status
SYS-01 | EXAMPLE - overwrite with your first system | B. Example | 2027-04-22 | 1 | 1 | 0 | 0 | 0 | 5 | 0% | At risk
7 - EQUIPMENT the planned commissioning start typed here drives every target date behind that equipment
Parent system | Equipment | Planned comm. start | Planned comm. finish | Actual start | Actual finish | Docs | Done | Late | Core missing | % done | Status | Key
SYS-01 | EQ-001 Example equipment item | 2027-04-22 | 2027-06-06 |  |  | 1 | 0 | 0 | 2 | 0% | At risk | 21.0001
8 - DOCUMENT TYPE LIBRARY
Document type | Phase | Core required (ATS) | Anchor milestone | Lead before anchor (days) | Default scope | Note | Core key
Basis of Commissioning | Pre-commissioning | Yes | Commissioning Start | 360 | All | T-12 months | 1
Surveillance Strategy | Pre-commissioning | Yes | Commissioning Start | 360 | All | T-12 months, ATS | 2
Surveillance Programme | Pre-commissioning | Yes | Commissioning Start | 270 | System | T-9 months, ATS | 3
Competency Evidence | Pre-commissioning | Yes | Commissioning Start | 270 | All | T-9 months, ATS | 4
Safe System Of Work | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS | 5
Risk Assessment And Method Statement | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS | 6
System Commissioning Programme | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS | 7
Commissioning Procedure | Pre-commissioning | Yes | Commissioning Start | 90 | Equipment | T-3 months, ATS | 8
Inspection and Test Plan | Pre-commissioning | Yes | Commissioning Start | 90 | Equipment | T-3 months, ATS | 9
Initial End Of Erection Status Report | Pre-commissioning | No | Commissioning Start | 90 | Equipment | T-3 months
Planned End Of Erection Status Report | Pre-commissioning | Yes | Commissioning Start | 30 | Equipment | T-1 month, ATS | 11
Authority To Start Evidence | Pre-commissioning | Yes | Commissioning Start | 14 | System | T-2 weeks, ATS | 12
Commissioning Results Sheet | Commissioning | No | Commissioning Finish | 0 | Equipment | During commissioning
Commissioning Phase Report | Post-commissioning | No | Functional Takeover | 15 | System | Anchor estimated
Handover Certificate | Post-commissioning | No | Functional Takeover | 0 | Equipment | Anchor estimated
Functional Takeover Package | Post-commissioning | No | Functional Takeover | 15 | System | Before FTC
Care And Maintenance Plan | Post-commissioning | No | Maintenance Transfer | 30 | System | Not in the spec lead table
Maintenance Transfer Package | Post-commissioning | No | Maintenance Transfer | 15 | System | Before TFM
Temporary Operations Transfer Package | Post-commissioning | No | Temporary Operations Transfer | 15 | System | Before TFTO
Final End Of Erection Status Report | Post-commissioning | No | Final Takeover | 15 | System | Before Final Takeover
Months are converted at 30 days each (T-3 months = 90), which reproduces the worked example in the source specification exactly. Post-commissioning types are anchored to a named milestone rather than to a guessed number of days.
9 - PHASES
Phase | Order
Pre-commissioning | 1
Commissioning | 2
Post-commissioning | 3
10 - PEOPLE feeds the Responsible, Approver and Owner dropdowns
Name | Role
A. Example | Commissioning Manager
B. Example | Commissioning Engineer
C. Example | Approver
Formulas:
Planned date = IF([Counts as]<>"",[Counts as],IF(OR([Status code]="",[Family]="",CTR_EARLIEST=""),"",CTR_EARLIEST+[Family]))
Planned date = IF([Status code]="","",IF(COUNTIFS(EQP_SYS,[Status code],EQP_START,">0")=0,"",SUMPRODUCT(MIN((EQP_SYS=[Status code])*(EQP_START>0)*EQP_START+((EQP_SYS=[Status code])*(EQP_START>0)=0)*2958465))))
Note on C15: Earliest planned commissioning start across all equipment in section 7. Every 'Commissioning Start' anchored target date ultimately derives from the start date of whatever the document covers, not from this single figure.
Note on D71: Type a date here to override the offset calculation for that milestone.
Note on K89: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K90: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K91: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K92: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K93: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K94: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K95: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K96: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K97: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K98: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K99: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K100: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K101: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K102: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K103: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K104: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K105: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K106: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K107: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K108: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K109: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K110: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K111: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K112: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K113: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.

## HOW IT WORKS
HOW IT WORKS
This workbook does not measure progress. It measures whether deliverables are on time against the commissioning start of whatever they cover.
THE ONE RULE
Target approval date | The earliest commissioning start among what the document covers (actual if known, otherwise planned), minus the lead time of its type. Post-commissioning types are measured back from their anchor milestone instead.
Days late | Positive = late. Negative = float. One convention everywhere.
Scope | All = the whole contract. System = one system. Equipment = one item. A document covering three systems is three rows.
START HERE
1. Contract and thresholds | SETUP sections 1 and 2.
2. Systems and equipment | SETUP sections 6 and 7. The planned commissioning start you type against each equipment item is what drives every target date behind it.
3. Check the type library | SETUP section 8. Phase, anchor milestone, lead time, core (ATS) flag and default scope for each type.
4. Enter deliverables | TRACKER. Pick a Type and a Scope; the target date appears.
5. Work the lists | DASHBOARD. In progress, Missing, Coming - documents and actions together.
READING THE TRACKER
Target override | Type a date to force a target the calculation cannot know - a cross-system dependency, a site event. The Source column then reads Manual. Clear the cell to fall back to Auto.
Source | Auto = calculated. Manual = you overrode it. Nothing is ever silently overwritten.
Check | Data-quality flag: scope not set, equipment not in that system, approved with no approval date. Empty means the row is clean.
Greyed cells | Not relevant for that row's scope. System is greyed for Scope = All; Equipment is greyed unless Scope = Equipment.
STATE COLOURS
Red | Late - the target approval date has passed.
Amber | At risk - due inside the document alert window.
Blue | In progress - an actual start date is filled in.
Pale amber | Coming - not started, due inside the horizon.
Green | Done - S4A reached, a P-code published, or an approval date entered.
Grey | Inactive - cancelled, revoked, superseded, transferred, destroyed.
Orange | Needs attention: scope not resolved, no target date, type not configured, or a data-quality flag.
WHAT 'MISSING' MEANS
Missing | A deliverable flagged Core required (ATS) in the library that does not exist as a row at all for a system or an equipment item. The workbook builds the expected matrix from the library and reports the gaps, ordered by when each would have been needed.
Covered by | A system-wide or contract-wide document counts as coverage for the equipment beneath it. Inactive documents do not count as coverage.
CAPACITY AND LIMITS
Rows | TRACKER 500 rows - ACTIONS 150 - systems 25 - equipment 80 - milestones 15 - core types tracked for gaps 12.
One flat table | The TRACKER is a single table, not one block per type. Capacity is shared: 500 rows go wherever they are needed, and you can filter or sort across every type at once.
To add rows | Copy the last data row and paste down, then widen the named ranges in Formulas > Name Manager.
No macros | Formulas only. Nothing to enable, nothing a corporate policy can block.
Excel version | Uses no function newer than Excel 2007, so it runs on any current corporate build.
ASSUMPTIONS
Months to days | 30 days per month (T-3 months = 90), which reproduces the worked example in the source specification exactly.
Post-commissioning anchors | Anchored to named milestones rather than to guessed day counts. Adjust the offsets in SETUP section 5.
Equipment with no date | If nothing behind a row has a commissioning start, the row reads 'Scope not resolved' rather than inventing a target.

## LISTS (hidden)
LISTS - staging. Generated automatically; do not edit.
Basis of Commissioning | All | 360 | Commissioning Start | Contract | Whole contract | Basis of Commissioning | 2026-04-27 | Document | DMIC-SYS-01-CPR-001 - Commissioning Procedure | EQ-001 Example equipment item | B. Example | 2027-01-22 | -150 |  | Done | 0 | Open | 1 | SYS-01 | 0 | 0 | Aug 26 | 0 | Done | All | Yes
Surveillance Strategy | All | 360 | Commissioning Start | Contract | Whole contract | Surveillance Strategy | 2026-04-27 | [7 empty] | In progress | 0 | In progress | 0 |  | 0 | 0 | Sep 26 | 0 | In progress | System | No
Surveillance Programme | System | 270 | Commissioning Start | [11 empty] | Late | 0 | On hold | 0 |  | 0 | 0 | Oct 26 | 0 | Inactive | Equipment
Competency Evidence | All | 270 | Commissioning Start | Contract | Whole contract | Competency Evidence | 2026-07-26 | [7 empty] | At risk | 0 | Done | 0 |  | 0 | 0 | Nov 26 | 0
Safe System Of Work | System | 180 | Commissioning Start | [11 empty] | Coming | 0 |  |  |  | 0 | 0 | Dec 26 | 0
Risk Assessment And Method Statement | System | 180 | Commissioning Start | [11 empty] | Not yet due | 1 |  |  |  | 0 | 0 | Jan 27 | 1
System Commissioning Programme | System | 180 | Commissioning Start | [11 empty] | Inactive | 0 |  |  |  | 0 | 0 | Feb 27 | 0
Commissioning Procedure | Equipment | 90 | Commissioning Start | [11 empty] | No target date | 0 |  |  |  | 0 | 0 | Mar 27 | 0
Inspection and Test Plan | Equipment | 90 | Commissioning Start | [16 empty] | 0 | 0 | Apr 27 | 0
Planned End Of Erection Status Report | Equipment | 30 | Commissioning Start | [16 empty] | 0 | 0 | May 27 | 0
Authority To Start Evidence | System | 14 | Commissioning Start | [16 empty] | 0 | 0 | Jun 27 | 0
[20 empty] | 0 | 0 | Jul 27 | 0
[20 empty] | 0 | 0
[20 empty] | 0 | 0
|  |  |  | System | SYS-01 | Surveillance Programme | 2026-07-26 | [12 empty] | 0 | 0
[20 empty] | 0 | 0
|  |  |  | System | SYS-01 | Safe System Of Work | 2026-10-24 | [12 empty] | 0 | 0
|  |  |  | System | SYS-01 | Risk Assessment And Method Statement | 2026-10-24 | [12 empty] | 0 | 0
|  |  |  | System | SYS-01 | System Commissioning Programme | 2026-10-24 | [12 empty] | 0 | 0
[20 empty] | 0 | 0
[20 empty] | 0 | 0
[20 empty] | 0 | 0
|  |  |  | System | SYS-01 | Authority To Start Evidence | 2027-04-08 | [12 empty] | 0 | 0
[20 empty] | 0 | 0
[20 empty] | 0 | 0
|  |  |  | Equipment | EQ-001 Example equipment item | Commissioning Procedure
|  |  |  | Equipment | EQ-001 Example equipment item | Inspection and Test Plan | 2027-01-22
|  |  |  | Equipment | EQ-001 Example equipment item | Planned End Of Erection Status Report | 2027-03-23
[8 empty] | Action | ACT-001 - EXAMPLE - overwrite with your first action | SYS-01 | B. Example | 2026-09-08 | -14 | -14