## DASHBOARD
COMMISSIONING DASHBOARD
DMIC Commissioning - Hinkley Point C - DMIC-HPC-04 ¦ what is late, what has never been created, what is coming.
CONTRACT STATUS
DELAYED |  |  | Worst item |  | DMIC-ALL-CPE-003 - Competency Evidence (210 d late - Whole contract)
|  |  | Share late |  | 8.929%
|  |  | Earliest commissioning start |  | 24-Oct-2026 in 60 d
|  |  | Core deliverables missing |  | 9
|  |  | Data quality flags |  | 0
PROGRESS
| Done | In progress | Late | Inactive | Missing | Total | % done
DOCUMENTS | 42 | 4 | 5 | 2 | 9 | 94 | 44.68%
ACTIONS | 1 | 3 | 5 | 2 | 0 | 18 | 5.556%
1. IN PROGRESS work started, or already late. Most late first. Showing 10 of 17
Kind | Subject | Scope | Owner | Target date | Days late
Document | DMIC-ALL-CPE-003 - Competency Evidence | Whole contract | D. Petrov | 2026-01-27 | 210 |  |  |  |  | 210
Document | DMIC-SYS-TP-IER-087 - Initial End Of Erection Status Report | TP-BSS-01 Bulk Supply Substation | D. Petrov | 2026-07-26 | 30 |  |  |  |  | 30.0001
Document | DMIC-SYS-TP-CPR-031 - Commissioning Procedure | TP-BSS-01 Bulk Supply Substation | R. Bellamy | 2026-07-26 | 30 |  |  |  |  | 30
Document | DMIC-SYS-TV-SVP-014 - Surveillance Programme | SYS-TV | L. Fontaine | 2026-07-26 | 30 |  |  |  |  | 30
Document | DMIC-SYS-SG-SSW-010 - Safe System Of Work | SYS-SG | C. Vasquez | 2026-07-26 | 30 |  |  |  |  | 30
Action | ACT-001 - Close out RAMS comments raised by the Client safety review | SYS-SG | D. Petrov | 2026-08-03 | 22 |  |  |  |  | 22
Action | ACT-002 - Obtain signed competency records for the ATP trackside team | SG-ATP-03 ATP Trackside Equipment | J. Whitfield | 2026-08-13 | 12 |  |  |  |  | 12
Action | ACT-003 - Resolve interlocking cabinet earthing non-conformance | SG-IXL-01 Interlocking Cabinet North | P. Nakamura | 2026-08-20 | 5 |  |  |  |  | 5
Action | ACT-010 - Submit Initial EESR for the signalling scope | SYS-SG | A. Mercer | 2026-08-22 | 3 |  |  |  |  | 3
Action | ACT-014 - Rectify jet fan vibration readings on Tunnel 1 | TV-JET-01 Jet Fan Array Tunnel 1 | J. Whitfield | 2026-08-24 | 1 |  |  |  |  | 1
2. MISSING core deliverables that do not exist yet. Soonest needed first. Showing 9 of 9
Level | Deliverable | Where | Needed by
Equipment | Commissioning Procedure | TP-TSS-03 Traction Substation Bravo | 2026-09-04 | [6 empty] | 46269.0003
System | System Commissioning Programme | SYS-CC | 2027-07-31 | [6 empty] | 46599.0001
Equipment | Planned End Of Erection Status Report | FA-SUP-03 Suppression Skid | 2027-08-15 | [6 empty] | 46614.0005
Equipment | Planned End Of Erection Status Report | LV-SWB-01 Main LV Switchboard | 2027-09-19 | [6 empty] | 46649.0005
Equipment | Inspection and Test Plan | LV-GEN-03 Standby Generator | 2027-09-24 | [6 empty] | 46654.0005
System | Authority To Start Evidence | SYS-LV | 2027-10-05 | [6 empty] | 46665.0001
Equipment | Commissioning Procedure | CC-HMI-02 Operator Workstations | 2027-11-28 | [6 empty] | 46719.0005
Equipment | Commissioning Procedure | CC-NET-03 Control Network Core | 2027-12-23 | [6 empty] | 46744.0005
System | Authority To Start Evidence | SYS-CC | 2028-01-13 | [6 empty] | 46765.0001
3. COMING not started, due inside the horizon set in SETUP. Soonest first. Showing 9 of 9
Kind | Subject | Scope | Owner | Target date | Days left
Action | ACT-004 - Issue System Commissioning Programme revision C for approval | SYS-TV | K. Rasmussen | 2026-08-27 | 2 |  |  |  |  | -2
Action | ACT-005 - Agree tunnel ventilation witnessing schedule with the Author | SYS-TV | R. Bellamy | 2026-09-03 | 9 |  |  |  |  | -9
Action | ACT-007 - Update Basis of Commissioning for the revised staging strate | - | M. Haddad | 2026-09-18 | 24 |  |  |  |  | -24
Action | ACT-008 - Mobilise second commissioning engineer for tunnel ventilatio | SYS-TV | C. Vasquez | 2026-09-25 | 31 |  |  |  |  | -31
Action | ACT-011 - Agree beneficial use conditions with Operations | SYS-TP | S. Okonkwo | 2026-10-08 | 44 |  |  |  |  | -44
Action | ACT-012 - Verify smoke extraction damper actuator supply | TV-SMK-03 Smoke Extraction Plant | L. Fontaine | 2026-10-15 | 51 |  |  |  |  | -51
Action | ACT-013 - Complete fire detection loop cause and effect matrix | FA-DET-02 Detection Loop Zone A | D. Petrov | 2026-10-24 | 60 |  |  |  |  | -60
Action | ACT-017 - Book UPS discharge test window with Operations | LV-UPS-02 UPS Room A | R. Bellamy | 2026-11-01 | 68 |  |  |  |  | -68
Action | ACT-016 - Confirm SCADA point list against the signalling interface | CC-SRV-01 SCADA Server Cluster | K. Rasmussen | 2026-11-08 | 75 |  |  |  |  | -75
4. BY SYSTEM
System | System name | Equip. | Docs | Done | Late | At risk | Core missing | % done | Status
SYS-TP | Traction Power & 33kV Distribution | 4 | 20 | 17 | 2 | 0 | 0 | 85% | Late
SYS-SG | Signalling & Train Control | 4 | 21 | 17 | 1 | 0 | 0 | 80.95% | Late
SYS-TV | Tunnel Ventilation | 3 | 16 | 6 | 1 | 0 | 0 | 37.5% | Late
SYS-FA | Fire Alarm & Detection | 3 | 13 | 0 | 0 | 0 | 0 | 0% | In progress
SYS-LV | LV Distribution & UPS | 3 | 11 | 0 | 0 | 0 | 1 | 0% | At risk
SYS-CC | Control Centre SCADA | 3 | 10 | 0 | 0 | 0 | 2 | 0% | At risk
5. EQUIPMENT TO WATCH most severe first
System | Equipment | Docs | Done | Late | Core missing | % done | Status
SYS-TP | TP-BSS-01 Bulk Supply Substation | 4 | 2 | 2 | 0 | 50% | Late |  |  | 2000.5001
SYS-CC | CC-NET-03 Control Network Core | 2 | 0 | 0 | 1 | 0% | At risk |  |  | 11.0001
SYS-CC | CC-HMI-02 Operator Workstations | 2 | 0 | 0 | 1 | 0% | At risk |  |  | 11.0001
SYS-LV | LV-GEN-03 Standby Generator | 2 | 0 | 0 | 1 | 0% | At risk |  |  | 11.0001
SYS-LV | LV-SWB-01 Main LV Switchboard | 2 | 0 | 0 | 1 | 0% | At risk |  |  | 11.0001
SYS-FA | FA-SUP-03 Suppression Skid | 2 | 0 | 0 | 1 | 0% | At risk |  |  | 11.0001
SYS-TP | TP-TSS-03 Traction Substation Bravo | 3 | 2 | 0 | 1 | 66.67% | At risk |  |  | 10.3335
SYS-CC | CC-SRV-01 SCADA Server Cluster | 3 | 0 | 0 | 0 | 0% | In progress |  |  | 1.0001
SYS-LV | LV-UPS-02 UPS Room A | 3 | 0 | 0 | 0 | 0% | In progress |  |  | 1.0001
SYS-FA | FA-DET-02 Detection Loop Zone A | 3 | 0 | 0 | 0 | 0% | In progress |  |  | 1.0001
SYS-FA | FA-PAN-01 Fire Panel Main | 3 | 0 | 0 | 0 | 0% | In progress |  |  | 1.0001
SYS-TV | TV-JET-01 Jet Fan Array Tunnel 1 | 4 | 1 | 0 | 0 | 25% | In progress |  |  | 0.75013
SYS-TV | TV-SMK-03 Smoke Extraction Plant | 3 | 1 | 0 | 0 | 33.33% | In progress |  |  | 0.66679
SYS-TV | TV-JET-02 Jet Fan Array Tunnel 2 | 4 | 2 | 0 | 0 | 50% | In progress |  |  | 0.50013
SYS-SG | SG-OCC-04 Signalling Workstations | 4 | 2 | 0 | 0 | 50% | In progress |  |  | 0.50012
6. MILESTONES
Milestone | Note | Planned date | Actual date | Days from today
Kick Off Meeting |  | 2025-10-29 |  | -300
Commissioning Readiness Review |  | 2026-08-25 |  | 0
Authority To Start |  | 2026-10-10 |  | 46
NTP |  | 2026-10-17 |  | 53
Commissioning Start |  | 2026-10-24 |  | 60
Commissioning Finish |  | 2027-04-22 |  | 240
Functional Takeover |  | 2027-05-07 |  | 255
Beneficial Use |  | 2027-05-17 |  | 265
Maintenance Transfer |  | 2027-06-01 |  | 280
Temporary Operations Transfer |  | 2027-06-16 |  | 295
Final Takeover |  | 2027-07-01 |  | 310
CHARTS

## TRACKER
DELIVERABLES TRACKER
One row per document per thing it covers: the whole contract (Scope = All), a system, or a piece of equipment. A document covering three systems is three rows. Fill Actual start when work begins. Days late: positive = late, negative = float.
Type | Scope | System | Equipment | Document no. | Responsible (drafting) | Approver | Status | Actual start | Target override | Target approval | Source | Actual approval | Days late | State | Check | Comment | Scope date | Auto target | Active | Done | Inactive | Phase | k late | k wip | k coming
Basis of Commissioning | All |  |  | DMIC-ALL-BOC-001 | S. Okonkwo | P. Nakamura | P1 - For Implementation |  |  | 2025-10-29 | Auto | 2025-10-25 | -4 | Done |  |  | 2026-10-24 | 2025-10-29 | 1 | 1 | 0 | Pre-commissioning
Surveillance Strategy | All |  |  | DMIC-ALL-SVS-002 | L. Fontaine | K. Rasmussen | P6 - For Construction |  |  | 2025-10-29 | Auto | 2025-10-26 | -3 | Done |  |  | 2026-10-24 | 2025-10-29 | 1 | 1 | 0 | Pre-commissioning
Competency Evidence | All |  |  | DMIC-ALL-CPE-003 | D. Petrov | R. Bellamy | S4B - Comments | 2025-12-10 |  | 2026-01-27 | Auto |  | 210 | Late |  |  | 2026-10-24 | 2026-01-27 | 1 | 0 | 0 | Pre-commissioning | 210 | 210
Surveillance Programme | System | SYS-TP |  | DMIC-SYS-TP-SVP-004 | J. Whitfield | N. Bergstrom | P1 - For Implementation |  |  | 2026-01-27 | Auto | 2026-01-26 | -1 | Done |  |  | 2026-10-24 | 2026-01-27 | 1 | 1 | 0 | Pre-commissioning
Safe System Of Work | System | SYS-TP |  | DMIC-SYS-TP-SSW-005 | P. Nakamura | M. Haddad | P6 - For Construction |  | 2026-09-15 | 2026-09-15 | Manual | 2026-04-27 | -141 | Done |  | Target moved by agreement - waiting on the SYS-SG interface package. | 2026-10-24 | 2026-04-27 | 1 | 1 | 0 | Pre-commissioning
Risk Assessment And Method Statement | System | SYS-TP |  | DMIC-SYS-TP-RAM-006 | K. Rasmussen | C. Vasquez | S4A - Approved |  |  | 2026-04-27 | Auto | 2026-04-28 | 1 | Done |  |  | 2026-10-24 | 2026-04-27 | 1 | 1 | 0 | Pre-commissioning
System Commissioning Programme | System | SYS-TP |  | DMIC-SYS-TP-SCP-007 | R. Bellamy | H. Lindqvist | P1 - For Implementation |  |  | 2026-04-27 | Auto | 2026-04-29 | 2 | Done |  |  | 2026-10-24 | 2026-04-27 | 1 | 1 | 0 | Pre-commissioning
Authority To Start Evidence | System | SYS-TP |  | DMIC-SYS-TP-ATS-008 | N. Bergstrom | A. Mercer | P6 - For Construction |  |  | 2026-10-10 | Auto | 2026-08-24 | -47 | Done |  |  | 2026-10-24 | 2026-10-10 | 1 | 1 | 0 | Pre-commissioning
Surveillance Programme | System | SYS-SG |  | DMIC-SYS-SG-SVP-009 | M. Haddad | S. Okonkwo | S4A - Approved |  |  | 2026-04-27 | Auto | 2026-05-01 | 4 | Done |  |  | 2027-01-22 | 2026-04-27 | 1 | 1 | 0 | Pre-commissioning
Safe System Of Work | System | SYS-SG |  | DMIC-SYS-SG-SSW-010 | C. Vasquez | L. Fontaine | S3 - For Review | 2026-06-01 |  | 2026-07-26 | Auto |  | 30 | Late |  |  | 2027-01-22 | 2026-07-26 | 1 | 0 | 0 | Pre-commissioning | 30 | 30
Risk Assessment And Method Statement | System | SYS-SG |  | DMIC-SYS-SG-RAM-011 | H. Lindqvist | D. Petrov | P6 - For Construction |  |  | 2026-07-26 | Auto | 2026-07-21 | -5 | Done |  |  | 2027-01-22 | 2026-07-26 | 1 | 1 | 0 | Pre-commissioning
System Commissioning Programme | System | SYS-SG |  | DMIC-SYS-SG-SCP-012 | A. Mercer | J. Whitfield | S4A - Approved |  |  | 2026-07-26 | Auto | 2026-07-22 | -4 | Done |  |  | 2027-01-22 | 2026-07-26 | 1 | 1 | 0 | Pre-commissioning
Authority To Start Evidence | System | SYS-SG |  | DMIC-SYS-SG-ATS-013 | S. Okonkwo | P. Nakamura | P1 - For Implementation |  |  | 2027-01-08 | Auto | 2026-08-19 | -142 | Done |  |  | 2027-01-22 | 2027-01-08 | 1 | 1 | 0 | Pre-commissioning
Surveillance Programme | System | SYS-TV |  | DMIC-SYS-TV-SVP-014 | L. Fontaine | K. Rasmussen | W1 - Draft | 2026-05-28 |  | 2026-07-26 | Auto |  | 30 | Late |  |  | 2027-04-22 | 2026-07-26 | 1 | 0 | 0 | Pre-commissioning | 30 | 30
Safe System Of Work | System | SYS-TV |  | DMIC-SYS-TV-SSW-015 | D. Petrov | R. Bellamy | S4A - Approved |  |  | 2026-10-24 | Auto | 2026-08-24 | -61 | Done |  |  | 2027-04-22 | 2026-10-24 | 1 | 1 | 0 | Pre-commissioning
Risk Assessment And Method Statement | System | SYS-TV |  | DMIC-SYS-TV-RAM-016 | J. Whitfield | N. Bergstrom | S4 - For Internal Approval | 2026-08-24 |  | 2026-10-24 | Auto |  | -60 | In progress |  |  | 2027-04-22 | 2026-10-24 | 1 | 0 | 0 | Pre-commissioning |  | -60
System Commissioning Programme | System | SYS-TV |  | DMIC-SYS-TV-SCP-017 | P. Nakamura | M. Haddad | S6 - For Acceptance | 2026-08-23 |  | 2026-10-24 | Auto |  | -60 | In progress |  |  | 2027-04-22 | 2026-10-24 | 1 | 0 | 0 | Pre-commissioning |  | -60
Authority To Start Evidence | System | SYS-TV |  | DMIC-SYS-TV-ATS-018 | K. Rasmussen | C. Vasquez | S4A - Approved |  |  | 2027-04-08 | Auto | 2026-08-21 | -230 | Done |  |  | 2027-04-22 | 2027-04-08 | 1 | 1 | 0 | Pre-commissioning
Surveillance Programme | System | SYS-FA |  | DMIC-SYS-FA-SVP-019 | R. Bellamy | H. Lindqvist | W1 - Draft | 2026-08-21 |  | 2026-10-24 | Auto |  | -60 | In progress |  |  | 2027-07-21 | 2026-10-24 | 1 | 0 | 0 | Pre-commissioning |  | -60
Safe System Of Work | System | SYS-FA |  | DMIC-SYS-FA-SSW-020 | N. Bergstrom | A. Mercer | S3 - For Review |  |  | 2027-01-22 | Auto |  | -150 | Not yet due |  |  | 2027-07-21 | 2027-01-22 | 1 | 0 | 0 | Pre-commissioning
Risk Assessment And Method Statement | System | SYS-FA |  | DMIC-SYS-FA-RAM-021 | M. Haddad | S. Okonkwo | S4 - For Internal Approval |  |  | 2027-01-22 | Auto |  | -150 | Not yet due |  |  | 2027-07-21 | 2027-01-22 | 1 | 0 | 0 | Pre-commissioning
System Commissioning Programme | System | SYS-FA |  | DMIC-SYS-FA-SCP-022 | C. Vasquez | L. Fontaine | S6 - For Acceptance |  |  | 2027-01-22 | Auto |  | -150 | Not yet due |  |  | 2027-07-21 | 2027-01-22 | 1 | 0 | 0 | Pre-commissioning
Authority To Start Evidence | System | SYS-FA |  | DMIC-SYS-FA-ATS-023 | H. Lindqvist | D. Petrov | S4B - Comments |  |  | 2027-07-07 | Auto |  | -316 | Not yet due |  |  | 2027-07-21 | 2027-07-07 | 1 | 0 | 0 | Pre-commissioning
Surveillance Programme | System | SYS-LV |  | DMIC-SYS-LV-SVP-024 | A. Mercer | J. Whitfield |  |  |  | 2027-01-22 | Auto |  | -150 | Not yet due |  |  | 2027-10-19 | 2027-01-22 | 1 | 0 | 0 | Pre-commissioning
Safe System Of Work | System | SYS-LV |  | DMIC-SYS-LV-SSW-025 | S. Okonkwo | P. Nakamura | W0 - Work In Progress |  |  | 2027-04-22 | Auto |  | -240 | Not yet due |  |  | 2027-10-19 | 2027-04-22 | 1 | 0 | 0 | Pre-commissioning
Risk Assessment And Method Statement | System | SYS-LV |  | DMIC-SYS-LV-RAM-026 | L. Fontaine | K. Rasmussen |  |  |  | 2027-04-22 | Auto |  | -240 | Not yet due |  |  | 2027-10-19 | 2027-04-22 | 1 | 0 | 0 | Pre-commissioning
System Commissioning Programme | System | SYS-LV |  | DMIC-SYS-LV-SCP-027 | D. Petrov | R. Bellamy |  |  |  | 2027-04-22 | Auto |  | -240 | Not yet due |  |  | 2027-10-19 | 2027-04-22 | 1 | 0 | 0 | Pre-commissioning
Surveillance Programme | System | SYS-CC |  | DMIC-SYS-CC-SVP-028 | J. Whitfield | N. Bergstrom |  |  |  | 2027-05-02 | Auto |  | -250 | Not yet due |  |  | 2028-01-27 | 2027-05-02 | 1 | 0 | 0 | Pre-commissioning
Safe System Of Work | System | SYS-CC |  | DMIC-SYS-CC-SSW-029 | P. Nakamura | M. Haddad |  |  |  | 2027-07-31 | Auto |  | -340 | Not yet due |  |  | 2028-01-27 | 2027-07-31 | 1 | 0 | 0 | Pre-commissioning
Risk Assessment And Method Statement | System | SYS-CC |  | DMIC-SYS-CC-RAM-030 | K. Rasmussen | C. Vasquez | W0 - Work In Progress |  |  | 2027-07-31 | Auto |  | -340 | Not yet due |  |  | 2028-01-27 | 2027-07-31 | 1 | 0 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-TP | TP-BSS-01 Bulk Supply Substation | DMIC-SYS-TP-CPR-031 | R. Bellamy | H. Lindqvist | S4 - For Internal Approval | 2026-05-31 |  | 2026-07-26 | Auto |  | 30 | Late |  |  | 2026-10-24 | 2026-07-26 | 1 | 0 | 0 | Pre-commissioning | 30 | 30
Inspection and Test Plan | Equipment | SYS-TP | TP-BSS-01 Bulk Supply Substation | DMIC-SYS-TP-ITP-032 | N. Bergstrom | A. Mercer | P6 - For Construction |  |  | 2026-07-26 | Auto | 2026-07-31 | 5 | Done |  |  | 2026-10-24 | 2026-07-26 | 1 | 1 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-TP | TP-BSS-01 Bulk Supply Substation | DMIC-SYS-TP-PER-033 | M. Haddad | S. Okonkwo | S4A - Approved |  |  | 2026-09-24 | Auto | 2026-08-20 | -35 | Done |  |  | 2026-10-24 | 2026-09-24 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-TP | TP-TSS-02 Traction Substation Alpha | DMIC-SYS-TP-CPR-034 | C. Vasquez | L. Fontaine | P1 - For Implementation |  |  | 2026-08-15 | Auto | 2026-08-11 | -4 | Done |  |  | 2026-11-13 | 2026-08-15 | 1 | 1 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-TP | TP-TSS-02 Traction Substation Alpha | DMIC-SYS-TP-ITP-035 | H. Lindqvist | D. Petrov | P6 - For Construction |  |  | 2026-08-15 | Auto | 2026-08-12 | -3 | Done |  |  | 2026-11-13 | 2026-08-15 | 1 | 1 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-TP | TP-TSS-02 Traction Substation Alpha | DMIC-SYS-TP-PER-036 | A. Mercer | J. Whitfield | S4A - Approved |  |  | 2026-10-14 | Auto | 2026-08-24 | -51 | Done |  |  | 2026-11-13 | 2026-10-14 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-TP | TP-TSS-03 Traction Substation Bravo | DMIC-SYS-TP-CPR-037 | S. Okonkwo | P. Nakamura | A2 - Superseded |  |  | 2026-09-04 | Auto | 2026-08-23 |  | Inactive |  |  | 2026-12-03 | 2026-09-04 | 0 | 0 | 1 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-TP | TP-TSS-03 Traction Substation Bravo | DMIC-SYS-TP-ITP-038 | L. Fontaine | K. Rasmussen | S4B - Comments | 2026-07-03 |  | 2026-09-04 | Auto |  | -10 | In progress |  |  | 2026-12-03 | 2026-09-04 | 1 | 0 | 0 | Pre-commissioning |  | -10
Planned End Of Erection Status Report | Equipment | SYS-TP | TP-TSS-03 Traction Substation Bravo | DMIC-SYS-TP-PER-039 | D. Petrov | R. Bellamy | S4A - Approved |  |  | 2026-11-03 | Auto | 2026-08-21 | -74 | Done |  |  | 2026-12-03 | 2026-11-03 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-TP | TP-OHL-04 Overhead Line Section A | DMIC-SYS-TP-CPR-040 | J. Whitfield | N. Bergstrom | P1 - For Implementation |  |  | 2026-09-19 | Auto | 2026-08-20 | -30 | Done |  |  | 2026-12-18 | 2026-09-19 | 1 | 1 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-TP | TP-OHL-04 Overhead Line Section A | DMIC-SYS-TP-ITP-041 | P. Nakamura | M. Haddad | P6 - For Construction |  |  | 2026-09-19 | Auto | 2026-08-19 | -31 | Done |  |  | 2026-12-18 | 2026-09-19 | 1 | 1 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-TP | TP-OHL-04 Overhead Line Section A | DMIC-SYS-TP-PER-042 | K. Rasmussen | C. Vasquez | S4A - Approved |  |  | 2026-11-18 | Auto | 2026-08-25 | -85 | Done |  |  | 2026-12-18 | 2026-11-18 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-SG | SG-IXL-01 Interlocking Cabinet North | DMIC-SYS-SG-CPR-043 | R. Bellamy | H. Lindqvist | P1 - For Implementation |  |  | 2026-10-24 | Auto | 2026-08-24 | -61 | Done |  |  | 2027-01-22 | 2026-10-24 | 1 | 1 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-SG | SG-IXL-01 Interlocking Cabinet North | DMIC-SYS-SG-ITP-044 | N. Bergstrom | A. Mercer | P6 - For Construction |  |  | 2026-10-24 | Auto | 2026-08-23 | -62 | Done |  |  | 2027-01-22 | 2026-10-24 | 1 | 1 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-SG | SG-IXL-01 Interlocking Cabinet North | DMIC-SYS-SG-PER-045 | M. Haddad | S. Okonkwo | S3 - For Review |  |  | 2026-12-23 | Auto |  | -120 | Not yet due |  |  | 2027-01-22 | 2026-12-23 | 1 | 0 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-SG | SG-IXL-02 Interlocking Cabinet South | DMIC-SYS-SG-CPR-046 | C. Vasquez | L. Fontaine | P1 - For Implementation |  |  | 2026-11-18 | Auto | 2026-08-21 | -89 | Done |  |  | 2027-02-16 | 2026-11-18 | 1 | 1 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-SG | SG-IXL-02 Interlocking Cabinet South | DMIC-SYS-SG-ITP-047 | H. Lindqvist | D. Petrov | P6 - For Construction |  |  | 2026-11-18 | Auto | 2026-08-20 | -90 | Done |  |  | 2027-02-16 | 2026-11-18 | 1 | 1 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-SG | SG-IXL-02 Interlocking Cabinet South | DMIC-SYS-SG-PER-048 | A. Mercer | J. Whitfield | S4A - Approved |  |  | 2027-01-17 | Auto | 2026-08-19 | -151 | Done |  |  | 2027-02-16 | 2027-01-17 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-SG | SG-ATP-03 ATP Trackside Equipment | DMIC-SYS-SG-CPR-049 | S. Okonkwo | P. Nakamura | P1 - For Implementation |  |  | 2026-12-08 | Auto | 2026-08-25 | -105 | Done |  |  | 2027-03-08 | 2026-12-08 | 1 | 1 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-SG | SG-ATP-03 ATP Trackside Equipment | DMIC-SYS-SG-ITP-050 | L. Fontaine | K. Rasmussen | P6 - For Construction |  |  | 2026-12-08 | Auto | 2026-08-24 | -106 | Done |  |  | 2027-03-08 | 2026-12-08 | 1 | 1 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-SG | SG-ATP-03 ATP Trackside Equipment | DMIC-SYS-SG-PER-051 | D. Petrov | R. Bellamy | S4A - Approved |  |  | 2027-02-06 | Auto | 2026-08-23 | -167 | Done |  |  | 2027-03-08 | 2027-02-06 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-SG | SG-OCC-04 Signalling Workstations | DMIC-SYS-SG-CPR-052 | J. Whitfield | N. Bergstrom | S6 - For Acceptance |  |  | 2027-01-02 | Auto |  | -130 | Not yet due |  |  | 2027-04-02 | 2027-01-02 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-SG | SG-OCC-04 Signalling Workstations | DMIC-SYS-SG-ITP-053 | P. Nakamura | M. Haddad | P6 - For Construction |  |  | 2027-01-02 | Auto | 2026-08-21 | -134 | Done |  |  | 2027-04-02 | 2027-01-02 | 1 | 1 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-SG | SG-OCC-04 Signalling Workstations | DMIC-SYS-SG-PER-054 | K. Rasmussen | C. Vasquez | S4A - Approved |  |  | 2027-03-03 | Auto | 2026-08-20 | -195 | Done |  |  | 2027-04-02 | 2027-03-03 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-TV | TV-JET-01 Jet Fan Array Tunnel 1 | DMIC-SYS-TV-CPR-055 | R. Bellamy | H. Lindqvist | S3 - For Review |  |  | 2027-01-22 | Auto |  | -150 | Not yet due |  |  | 2027-04-22 | 2027-01-22 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-TV | TV-JET-01 Jet Fan Array Tunnel 1 | DMIC-SYS-TV-ITP-056 | N. Bergstrom | A. Mercer | S4 - For Internal Approval |  |  | 2027-01-22 | Auto |  | -150 | Not yet due |  |  | 2027-04-22 | 2027-01-22 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-TV | TV-JET-01 Jet Fan Array Tunnel 1 | DMIC-SYS-TV-PER-057 | M. Haddad | S. Okonkwo | S4A - Approved |  |  | 2027-03-23 | Auto | 2026-08-24 | -211 | Done |  |  | 2027-04-22 | 2027-03-23 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-TV | TV-JET-02 Jet Fan Array Tunnel 2 | DMIC-SYS-TV-CPR-058 | C. Vasquez | L. Fontaine | S4B - Comments |  |  | 2027-02-21 | Auto |  | -180 | Not yet due |  |  | 2027-05-22 | 2027-02-21 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-TV | TV-JET-02 Jet Fan Array Tunnel 2 | DMIC-SYS-TV-ITP-059 | H. Lindqvist | D. Petrov | W1 - Draft |  |  | 2027-02-21 | Auto |  | -180 | Not yet due |  |  | 2027-05-22 | 2027-02-21 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-TV | TV-JET-02 Jet Fan Array Tunnel 2 | DMIC-SYS-TV-PER-060 | A. Mercer | J. Whitfield | S4A - Approved |  |  | 2027-04-22 | Auto | 2026-08-21 | -244 | Done |  |  | 2027-05-22 | 2027-04-22 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-TV | TV-SMK-03 Smoke Extraction Plant | DMIC-SYS-TV-CPR-061 | S. Okonkwo | P. Nakamura | S4 - For Internal Approval |  |  | 2027-03-23 | Auto |  | -210 | Not yet due |  |  | 2027-06-21 | 2027-03-23 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-TV | TV-SMK-03 Smoke Extraction Plant | DMIC-SYS-TV-ITP-062 | L. Fontaine | K. Rasmussen | S6 - For Acceptance |  |  | 2027-03-23 | Auto |  | -210 | Not yet due |  |  | 2027-06-21 | 2027-03-23 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-TV | TV-SMK-03 Smoke Extraction Plant | DMIC-SYS-TV-PER-063 | D. Petrov | R. Bellamy | S4A - Approved |  |  | 2027-05-22 | Auto | 2026-08-25 | -270 | Done |  |  | 2027-06-21 | 2027-05-22 | 1 | 1 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-FA | FA-PAN-01 Fire Panel Main | DMIC-SYS-FA-CPR-064 | J. Whitfield | N. Bergstrom | W1 - Draft |  |  | 2027-04-22 | Auto |  | -240 | Not yet due |  |  | 2027-07-21 | 2027-04-22 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-FA | FA-PAN-01 Fire Panel Main | DMIC-SYS-FA-ITP-065 | P. Nakamura | M. Haddad | S3 - For Review |  |  | 2027-04-22 | Auto |  | -240 | Not yet due |  |  | 2027-07-21 | 2027-04-22 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-FA | FA-PAN-01 Fire Panel Main | DMIC-SYS-FA-PER-066 | K. Rasmussen | C. Vasquez | S4 - For Internal Approval |  |  | 2027-06-21 | Auto |  | -300 | Not yet due |  |  | 2027-07-21 | 2027-06-21 | 1 | 0 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-FA | FA-DET-02 Detection Loop Zone A | DMIC-SYS-FA-CPR-067 | R. Bellamy | H. Lindqvist | S6 - For Acceptance |  |  | 2027-05-22 | Auto |  | -270 | Not yet due |  |  | 2027-08-20 | 2027-05-22 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-FA | FA-DET-02 Detection Loop Zone A | DMIC-SYS-FA-ITP-068 | N. Bergstrom | A. Mercer | S4B - Comments |  |  | 2027-05-22 | Auto |  | -270 | Not yet due |  |  | 2027-08-20 | 2027-05-22 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-FA | FA-DET-02 Detection Loop Zone A | DMIC-SYS-FA-PER-069 | M. Haddad | S. Okonkwo | W1 - Draft |  |  | 2027-07-21 | Auto |  | -330 | Not yet due |  |  | 2027-08-20 | 2027-07-21 | 1 | 0 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-FA | FA-SUP-03 Suppression Skid | DMIC-SYS-FA-CPR-070 | C. Vasquez | L. Fontaine | S3 - For Review |  |  | 2027-06-16 | Auto |  | -295 | Not yet due |  |  | 2027-09-14 | 2027-06-16 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-FA | FA-SUP-03 Suppression Skid | DMIC-SYS-FA-ITP-071 | H. Lindqvist | D. Petrov | S4 - For Internal Approval |  |  | 2027-06-16 | Auto |  | -295 | Not yet due |  |  | 2027-09-14 | 2027-06-16 | 1 | 0 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-LV | LV-SWB-01 Main LV Switchboard | DMIC-SYS-LV-CPR-072 | A. Mercer | J. Whitfield |  |  |  | 2027-07-21 | Auto |  | -330 | Not yet due |  |  | 2027-10-19 | 2027-07-21 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-LV | LV-SWB-01 Main LV Switchboard | DMIC-SYS-LV-ITP-073 | S. Okonkwo | P. Nakamura |  |  |  | 2027-07-21 | Auto |  | -330 | Not yet due |  |  | 2027-10-19 | 2027-07-21 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-LV | LV-SWB-01 Main LV Switchboard | DMIC-SYS-LV-PER-074 | L. Fontaine | K. Rasmussen | A2 - Superseded |  |  | 2027-09-19 | Auto |  |  | Inactive |  |  | 2027-10-19 | 2027-09-19 | 0 | 0 | 1 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-LV | LV-UPS-02 UPS Room A | DMIC-SYS-LV-CPR-075 | D. Petrov | R. Bellamy | W0 - Work In Progress |  |  | 2027-08-25 | Auto |  | -365 | Not yet due |  |  | 2027-11-23 | 2027-08-25 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-LV | LV-UPS-02 UPS Room A | DMIC-SYS-LV-ITP-076 | J. Whitfield | N. Bergstrom |  |  |  | 2027-08-25 | Auto |  | -365 | Not yet due |  |  | 2027-11-23 | 2027-08-25 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-LV | LV-UPS-02 UPS Room A | DMIC-SYS-LV-PER-077 | P. Nakamura | M. Haddad |  |  |  | 2027-10-24 | Auto |  | -425 | Not yet due |  |  | 2027-11-23 | 2027-10-24 | 1 | 0 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-LV | LV-GEN-03 Standby Generator | DMIC-SYS-LV-CPR-078 | K. Rasmussen | C. Vasquez |  |  |  | 2027-09-24 | Auto |  | -395 | Not yet due |  |  | 2027-12-23 | 2027-09-24 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-LV | LV-GEN-03 Standby Generator | DMIC-SYS-LV-PER-079 | R. Bellamy | H. Lindqvist |  |  |  | 2027-11-23 | Auto |  | -455 | Not yet due |  |  | 2027-12-23 | 2027-11-23 | 1 | 0 | 0 | Pre-commissioning
Commissioning Procedure | Equipment | SYS-CC | CC-SRV-01 SCADA Server Cluster | DMIC-SYS-CC-CPR-080 | N. Bergstrom | A. Mercer | W0 - Work In Progress |  |  | 2027-10-29 | Auto |  | -430 | Not yet due |  |  | 2028-01-27 | 2027-10-29 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-CC | CC-SRV-01 SCADA Server Cluster | DMIC-SYS-CC-ITP-081 | M. Haddad | S. Okonkwo |  |  |  | 2027-10-29 | Auto |  | -430 | Not yet due |  |  | 2028-01-27 | 2027-10-29 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-CC | CC-SRV-01 SCADA Server Cluster | DMIC-SYS-CC-PER-082 | C. Vasquez | L. Fontaine |  |  |  | 2027-12-28 | Auto |  | -490 | Not yet due |  |  | 2028-01-27 | 2027-12-28 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-CC | CC-HMI-02 Operator Workstations | DMIC-SYS-CC-ITP-083 | H. Lindqvist | D. Petrov |  |  |  | 2027-11-28 | Auto |  | -460 | Not yet due |  |  | 2028-02-26 | 2027-11-28 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-CC | CC-HMI-02 Operator Workstations | DMIC-SYS-CC-PER-084 | A. Mercer | J. Whitfield |  |  |  | 2028-01-27 | Auto |  | -520 | Not yet due |  |  | 2028-02-26 | 2028-01-27 | 1 | 0 | 0 | Pre-commissioning
Inspection and Test Plan | Equipment | SYS-CC | CC-NET-03 Control Network Core | DMIC-SYS-CC-ITP-085 | S. Okonkwo | P. Nakamura | W0 - Work In Progress |  |  | 2027-12-23 | Auto |  | -485 | Not yet due |  |  | 2028-03-22 | 2027-12-23 | 1 | 0 | 0 | Pre-commissioning
Planned End Of Erection Status Report | Equipment | SYS-CC | CC-NET-03 Control Network Core | DMIC-SYS-CC-PER-086 | L. Fontaine | K. Rasmussen |  |  |  | 2028-02-21 | Auto |  | -545 | Not yet due |  |  | 2028-03-22 | 2028-02-21 | 1 | 0 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-TP | TP-BSS-01 Bulk Supply Substation | DMIC-SYS-TP-IER-087 | D. Petrov | R. Bellamy | S6 - For Acceptance | 2026-06-04 |  | 2026-07-26 | Auto |  | 30 | Late |  |  | 2026-10-24 | 2026-07-26 | 1 | 0 | 0 | Pre-commissioning | 30.0001 | 30.0001
Initial End Of Erection Status Report | Equipment | SYS-TP | TP-TSS-02 Traction Substation Alpha | DMIC-SYS-TP-IER-088 | J. Whitfield | N. Bergstrom | P1 - For Implementation |  |  | 2026-08-15 | Auto | 2026-08-10 | -5 | Done |  |  | 2026-11-13 | 2026-08-15 | 1 | 1 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-TP | TP-TSS-03 Traction Substation Bravo | DMIC-SYS-TP-IER-089 | P. Nakamura | M. Haddad | P6 - For Construction |  |  | 2026-09-04 | Auto | 2026-08-20 | -15 | Done |  |  | 2026-12-03 | 2026-09-04 | 1 | 1 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-TP | TP-OHL-04 Overhead Line Section A | DMIC-SYS-TP-IER-090 | K. Rasmussen | C. Vasquez | S4A - Approved |  |  | 2026-09-19 | Auto | 2026-08-19 | -31 | Done |  |  | 2026-12-18 | 2026-09-19 | 1 | 1 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-SG | SG-IXL-01 Interlocking Cabinet North | DMIC-SYS-SG-IER-091 | R. Bellamy | H. Lindqvist | P1 - For Implementation |  |  | 2026-10-24 | Auto | 2026-08-25 | -60 | Done |  |  | 2027-01-22 | 2026-10-24 | 1 | 1 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-SG | SG-IXL-02 Interlocking Cabinet South | DMIC-SYS-SG-IER-092 | N. Bergstrom | A. Mercer | P6 - For Construction |  |  | 2026-11-18 | Auto | 2026-08-24 | -86 | Done |  |  | 2027-02-16 | 2026-11-18 | 1 | 1 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-SG | SG-ATP-03 ATP Trackside Equipment | DMIC-SYS-SG-IER-093 | M. Haddad | S. Okonkwo | S4A - Approved |  |  | 2026-12-08 | Auto | 2026-08-23 | -107 | Done |  |  | 2027-03-08 | 2026-12-08 | 1 | 1 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-SG | SG-OCC-04 Signalling Workstations | DMIC-SYS-SG-IER-094 | C. Vasquez | L. Fontaine | W1 - Draft |  |  | 2027-01-02 | Auto |  | -130 | Not yet due |  |  | 2027-04-02 | 2027-01-02 | 1 | 0 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-TV | TV-JET-01 Jet Fan Array Tunnel 1 | DMIC-SYS-TV-IER-095 | H. Lindqvist | D. Petrov | S3 - For Review |  |  | 2027-01-22 | Auto |  | -150 | Not yet due |  |  | 2027-04-22 | 2027-01-22 | 1 | 0 | 0 | Pre-commissioning
Initial End Of Erection Status Report | Equipment | SYS-TV | TV-JET-02 Jet Fan Array Tunnel 2 | DMIC-SYS-TV-IER-096 | A. Mercer | J. Whitfield | S4A - Approved |  |  | 2027-02-21 | Auto | 2026-08-20 | -185 | Done |  |  | 2027-05-22 | 2027-02-21 | 1 | 1 | 0 | Pre-commissioning
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
[19 empty] | 0 | 0 | 0
Formulas:
Target approval = IF([Type]="","",IF([Target override]<>"",[Target override],[Auto target]))
Days late = IF([Active]=0,"",IF([Done]=1,IF([Actual approval]="","",[Actual approval]-[Target approval]),IF([Target approval]="","",TODAY()-[Target approval])))
Scope date = IF(OR([Type]="",[Scope]=""),"",IF([Scope]="Equipment",IFERROR(INDEX(EQP_START,MATCH([Equipment],EQP_NOM,0)),""),IF([Scope]="System",IFERROR(INDEX(SYS_EARLIEST,MATCH([System],SYS_ID,0)),""),IF([Scope]="All",CTR_EARLIEST,""))))
Note on J3: Type a date here only when the automatic calculation cannot know something - a cross-system dependency, a site event. The Source column then reads Manual. Clear this cell to fall back to the automatic date.
Note on K3: Automatic = the commissioning start of whatever this row covers (actual if known, otherwise planned), minus the lead time of the type. Post-commissioning types are measured back from their anchor milestone instead.

## ACTIONS
ACTIONS
One filterable table. Link an action to a system, an equipment item, a document, any combination, or nothing at all - every link is optional.
Action ID | Description | Phase | System | Equipment | Document no. | Owner | Actual start | Due date | Done date | Status | Days late | State | Comment | k late | k wip | k coming
ACT-001 | Close out RAMS comments raised by the Client safety review | Pre-commissioning | SYS-SG |  |  | D. Petrov | 2026-07-14 | 2026-08-03 |  | In progress | 22 | Late |  | 22 | 22
ACT-002 | Obtain signed competency records for the ATP trackside team | Pre-commissioning | SYS-SG | SG-ATP-03 ATP Trackside Equipment |  | J. Whitfield |  | 2026-08-13 |  | Open | 12 | Late |  | 12 | 12
ACT-003 | Resolve interlocking cabinet earthing non-conformance | Pre-commissioning | SYS-SG | SG-IXL-01 Interlocking Cabinet North |  | P. Nakamura | 2026-07-31 | 2026-08-20 |  | In progress | 5 | Late |  | 5 | 5
ACT-004 | Issue System Commissioning Programme revision C for approval | Pre-commissioning | SYS-TV |  |  | K. Rasmussen |  | 2026-08-27 |  | Open | -2 | At risk |  |  |  | -2
ACT-005 | Agree tunnel ventilation witnessing schedule with the Authority | Pre-commissioning | SYS-TV |  |  | R. Bellamy |  | 2026-09-03 |  | Open | -9 | Coming |  |  |  | -9
ACT-006 | Confirm 33kV protection settings against the final study | Pre-commissioning | SYS-TP | TP-TSS-03 Traction Substation Bravo |  | N. Bergstrom | 2026-08-21 | 2026-09-10 |  | In progress | -16 | In progress |  |  | -16
ACT-007 | Update Basis of Commissioning for the revised staging strategy | Pre-commissioning |  |  |  | M. Haddad |  | 2026-09-18 |  | On hold | -24 | Coming |  |  |  | -24
ACT-008 | Mobilise second commissioning engineer for tunnel ventilation | Pre-commissioning | SYS-TV |  |  | C. Vasquez |  | 2026-09-25 |  | Open | -31 | Coming |  |  |  | -31
ACT-009 | Close punch list items on Traction Substation Alpha | Pre-commissioning | SYS-TP | TP-TSS-02 Traction Substation Alpha |  | H. Lindqvist | 2026-08-17 | 2026-09-06 |  | In progress | -12 | In progress |  |  | -12
ACT-010 | Submit Initial EESR for the signalling scope | Pre-commissioning | SYS-SG |  |  | A. Mercer |  | 2026-08-22 |  | Open | 3 | Late |  | 3 | 3
ACT-011 | Agree beneficial use conditions with Operations | Pre-commissioning | SYS-TP |  |  | S. Okonkwo |  | 2026-10-08 |  | On hold | -44 | Coming |  |  |  | -44
ACT-012 | Verify smoke extraction damper actuator supply | Pre-commissioning | SYS-TV | TV-SMK-03 Smoke Extraction Plant |  | L. Fontaine |  | 2026-10-15 |  | Open | -51 | Coming |  |  |  | -51
ACT-013 | Complete fire detection loop cause and effect matrix | Pre-commissioning | SYS-FA | FA-DET-02 Detection Loop Zone A |  | D. Petrov |  | 2026-10-24 |  | Open | -60 | Coming |  |  |  | -60
ACT-014 | Rectify jet fan vibration readings on Tunnel 1 | Pre-commissioning | SYS-TV | TV-JET-01 Jet Fan Array Tunnel 1 |  | J. Whitfield | 2026-08-04 | 2026-08-24 |  | In progress | 1 | Late |  | 1 | 1
ACT-015 | Archive approved bulk supply substation records | Pre-commissioning | SYS-TP | TP-BSS-01 Bulk Supply Substation |  | P. Nakamura | 2026-07-06 | 2026-07-26 | 2026-07-24 | Done | -2 | Done
ACT-016 | Confirm SCADA point list against the signalling interface | Pre-commissioning | SYS-CC | CC-SRV-01 SCADA Server Cluster |  | K. Rasmussen |  | 2026-11-08 |  | Open | -75 | Coming |  |  |  | -75
ACT-017 | Book UPS discharge test window with Operations | Pre-commissioning | SYS-LV | LV-UPS-02 UPS Room A |  | R. Bellamy |  | 2026-11-01 |  | Open | -68 | Coming |  |  |  | -68
ACT-018 | Issue Authority To Start evidence pack for traction power | Pre-commissioning | SYS-TP |  |  | N. Bergstrom | 2026-08-11 | 2026-08-31 |  | In progress | -6 | In progress |  |  | -6
Formulas:
Days late = IF([Action ID]="","",IF([Status]=A_DONE,IF([Done date]="","",[Done date]-[Due date]),IF([Due date]="","",TODAY()-[Due date])))

## SETUP
SETUP - CONTROL PANEL
Everything in the workbook is driven from this sheet. Blue cells are yours to edit; grey cells calculate themselves. Nothing else needs rebuilding.
1 - CONTRACT
Contract number | DMIC-HPC-04
Contract name | DMIC Commissioning - Hinkley Point C
Contract Manager | A. Mercer
Commissioning Manager | S. Okonkwo
Quality Lead | L. Fontaine
2 - THRESHOLDS
Document alert window (days) | 30 | An unapproved document turns At risk inside this many days before its target.
Action alert window (days) | 3 | Same idea, for actions.
Coming horizon (days) | 90 | How far ahead the COMING block looks.
Earliest commissioning start (calculated) | 2026-10-24 | Drives the milestone dates in section 5.
3 - WORDING rename anything here: the whole workbook follows
Document approved (S4A reached) or published | Done
Target approval date passed without approval | Late
Actual start filled in, not late | In progress
Due inside the document alert window | At risk
Due inside the coming horizon, not started | Coming
Due beyond the horizon | Not yet due
Cancelled, revoked, superseded, transferred, destroyed | Inactive
Actions only: due beyond the action alert window | On track
No commissioning start date behind this row | Scope not resolved
Anchor milestone has no date | No target date
Type missing from the library | Type not configured
Actions only: due date not filled in | No due date
3b - CONTRACT STATUS WORDING
At least one document or action is late | DELAYED
Nothing late, but something is at risk or missing | AT RISK OF DELAY
Nothing late, nothing at risk | ON SCHEDULE
3c - ACTION STATUS WORDING
Action status 1 | Open
Action status 2 | In progress
Action status 3 | On hold
Action status 4 | Done
4 - DOCUMENT STATUS CODES 'Counts as' is how each code is read everywhere else
Status code | Family | Counts as
W0 - Work In Progress | Preparation | In progress
W1 - Draft | Preparation | In progress
W2 - Revoked | Preparation | Inactive
S2 - For Information | Review | In progress
S3 - For Review | Review | In progress
S4 - For Internal Approval | Review | In progress
S4A - Approved | Approval result | Done
S4B - Comments | Approval result | In progress
S4C - Rejected | Approval result | In progress
S6 - For Acceptance | Acceptance | In progress
S6Q - Quality Checked | Acceptance | In progress
S6B - Comments | Acceptance | In progress
S6C - Rejected | Acceptance | In progress
P1 - For Implementation | Published | Done
P2 - For Costing | Published | Done
P3 - For Tender | Published | Done
P4 - For Contractor Design | Published | Done
P5 - For Manufacture / Procurement | Published | Done
P6 - For Construction | Published | Done
P7 - As-Built | Published | Done
A1 - Cancelled | Closed | Inactive
A2 - Superseded | Closed | Inactive
A3 - Transferred | Closed | Inactive
A4 - Destroyed | Closed | Inactive
S4A and the P-codes stop the delay counter. A-codes and W2 are Inactive: they leave every active counter, stay visible in their own column, and no longer count as coverage for a required deliverable.
5 - MILESTONES dates only; anything to organise goes in ACTIONS
Milestone | Offset from earliest start (days) | Date typed (optional) | Planned date | Actual date | Note
Kick Off Meeting | -360 |  | 2025-10-29
Commissioning Readiness Review | -60 |  | 2026-08-25
Authority To Start | -14 |  | 2026-10-10
NTP | -7 |  | 2026-10-17
Commissioning Start | 0 |  | 2026-10-24
Commissioning Finish | 180 |  | 2027-04-22
Functional Takeover | 195 |  | 2027-05-07
Beneficial Use | 205 |  | 2027-05-17
Maintenance Transfer | 220 |  | 2027-06-01
Temporary Operations Transfer | 235 |  | 2027-06-16
Final Takeover | 250 |  | 2027-07-01
6 - SYSTEMS
System ID | System name | Commissioning Engineer | Earliest equipment start | Equip. | Docs | Done | Late | At risk | Core missing | % done | Status
SYS-TP | Traction Power & 33kV Distribution | D. Petrov | 2026-10-24 | 4 | 20 | 17 | 2 | 0 | 0 | 85% | Late
SYS-SG | Signalling & Train Control | J. Whitfield | 2027-01-22 | 4 | 21 | 17 | 1 | 0 | 0 | 80.95% | Late
SYS-TV | Tunnel Ventilation | P. Nakamura | 2027-04-22 | 3 | 16 | 6 | 1 | 0 | 0 | 37.5% | Late
SYS-FA | Fire Alarm & Detection | K. Rasmussen | 2027-07-21 | 3 | 13 | 0 | 0 | 0 | 0 | 0% | In progress
SYS-LV | LV Distribution & UPS | R. Bellamy | 2027-10-19 | 3 | 11 | 0 | 0 | 0 | 1 | 0% | At risk
SYS-CC | Control Centre SCADA | N. Bergstrom | 2028-01-27 | 3 | 10 | 0 | 0 | 0 | 2 | 0% | At risk
7 - EQUIPMENT the planned commissioning start typed here drives every target date behind that equipment
Parent system | Equipment | Planned comm. start | Planned comm. finish | Actual start | Actual finish | Docs | Done | Late | Core missing | % done | Status | Key
SYS-TP | TP-BSS-01 Bulk Supply Substation | 2026-10-24 | 2026-12-08 |  |  | 4 | 2 | 2 | 0 | 50% | Late | 2000.5001
SYS-TP | TP-TSS-02 Traction Substation Alpha | 2026-11-13 | 2026-12-28 |  |  | 4 | 4 | 0 | 0 | 100% | Done | 0.000118
SYS-TP | TP-TSS-03 Traction Substation Bravo | 2026-12-03 | 2027-01-17 |  |  | 3 | 2 | 0 | 1 | 66.67% | At risk | 10.3335
SYS-TP | TP-OHL-04 Overhead Line Section A | 2026-12-18 | 2027-02-01 |  |  | 4 | 4 | 0 | 0 | 100% | Done | 0.00012
SYS-SG | SG-IXL-01 Interlocking Cabinet North | 2027-01-22 | 2027-03-08 |  |  | 4 | 3 | 0 | 0 | 75% | In progress | 0.25012
SYS-SG | SG-IXL-02 Interlocking Cabinet South | 2027-02-16 | 2027-04-02 |  |  | 4 | 4 | 0 | 0 | 100% | Done | 0.000122
SYS-SG | SG-ATP-03 ATP Trackside Equipment | 2027-03-08 | 2027-04-22 |  |  | 4 | 4 | 0 | 0 | 100% | Done | 0.000123
SYS-SG | SG-OCC-04 Signalling Workstations | 2027-04-02 | 2027-05-17 |  |  | 4 | 2 | 0 | 0 | 50% | In progress | 0.50012
SYS-TV | TV-JET-01 Jet Fan Array Tunnel 1 | 2027-04-22 | 2027-06-06 |  |  | 4 | 1 | 0 | 0 | 25% | In progress | 0.75013
SYS-TV | TV-JET-02 Jet Fan Array Tunnel 2 | 2027-05-22 | 2027-07-06 |  |  | 4 | 2 | 0 | 0 | 50% | In progress | 0.50013
SYS-TV | TV-SMK-03 Smoke Extraction Plant | 2027-06-21 | 2027-08-05 |  |  | 3 | 1 | 0 | 0 | 33.33% | In progress | 0.66679
SYS-FA | FA-PAN-01 Fire Panel Main | 2027-07-21 | 2027-09-04 |  |  | 3 | 0 | 0 | 0 | 0% | In progress | 1.0001
SYS-FA | FA-DET-02 Detection Loop Zone A | 2027-08-20 | 2027-10-04 |  |  | 3 | 0 | 0 | 0 | 0% | In progress | 1.0001
SYS-FA | FA-SUP-03 Suppression Skid | 2027-09-14 | 2027-10-29 |  |  | 2 | 0 | 0 | 1 | 0% | At risk | 11.0001
SYS-LV | LV-SWB-01 Main LV Switchboard | 2027-10-19 | 2027-12-03 |  |  | 2 | 0 | 0 | 1 | 0% | At risk | 11.0001
SYS-LV | LV-UPS-02 UPS Room A | 2027-11-23 | 2028-01-07 |  |  | 3 | 0 | 0 | 0 | 0% | In progress | 1.0001
SYS-LV | LV-GEN-03 Standby Generator | 2027-12-23 | 2028-02-06 |  |  | 2 | 0 | 0 | 1 | 0% | At risk | 11.0001
SYS-CC | CC-SRV-01 SCADA Server Cluster | 2028-01-27 | 2028-03-12 |  |  | 3 | 0 | 0 | 0 | 0% | In progress | 1.0001
SYS-CC | CC-HMI-02 Operator Workstations | 2028-02-26 | 2028-04-11 |  |  | 2 | 0 | 0 | 1 | 0% | At risk | 11.0001
SYS-CC | CC-NET-03 Control Network Core | 2028-03-22 | 2028-05-06 |  |  | 2 | 0 | 0 | 1 | 0% | At risk | 11.0001
8 - DOCUMENT TYPE LIBRARY
Document type | Phase | Core required (ATS) | Anchor milestone | Lead before anchor (days) | Default scope | Note | Core key
Basis of Commissioning | Pre-commissioning | Yes | Commissioning Start | 360 | All | T-12 months | 1
Surveillance Strategy | Pre-commissioning | Yes | Commissioning Start | 360 | All | T-12 months, ATS | 2
Surveillance Programme | Pre-commissioning | Yes | Commissioning Start | 270 | System | T-9 months, ATS | 3
Competency Evidence | Pre-commissioning | Yes | Commissioning Start | 270 | All | T-9 months, ATS | 4
Safe System Of Work | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS | 5
Risk Assessment And Method Statement | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS | 6
System Commissioning Programme | Pre-commissioning | Yes | Commissioning Start | 180 | System | T-6 months, ATS | 7
Commissioning Procedure | Pre-commissioning | Yes | Commissioning Start | 90 | Equipment | T-3 months, ATS | 8
Inspection and Test Plan | Pre-commissioning | Yes | Commissioning Start | 90 | Equipment | T-3 months, ATS | 9
Initial End Of Erection Status Report | Pre-commissioning | No | Commissioning Start | 90 | Equipment | T-3 months
Planned End Of Erection Status Report | Pre-commissioning | Yes | Commissioning Start | 30 | Equipment | T-1 month, ATS | 11
Authority To Start Evidence | Pre-commissioning | Yes | Commissioning Start | 14 | System | T-2 weeks, ATS | 12
Commissioning Results Sheet | Commissioning | No | Commissioning Finish | 0 | Equipment | During commissioning
Commissioning Phase Report | Post-commissioning | No | Functional Takeover | 15 | System | Anchor estimated
Handover Certificate | Post-commissioning | No | Functional Takeover | 0 | Equipment | Anchor estimated
Functional Takeover Package | Post-commissioning | No | Functional Takeover | 15 | System | Before FTC
Care And Maintenance Plan | Post-commissioning | No | Maintenance Transfer | 30 | System | Not in the spec lead table
Maintenance Transfer Package | Post-commissioning | No | Maintenance Transfer | 15 | System | Before TFM
Temporary Operations Transfer Package | Post-commissioning | No | Temporary Operations Transfer | 15 | System | Before TFTO
Final End Of Erection Status Report | Post-commissioning | No | Final Takeover | 15 | System | Before Final Takeover
Months are converted at 30 days each (T-3 months = 90), which reproduces the worked example in the source specification exactly. Post-commissioning types are anchored to a named milestone rather than to a guessed number of days.
9 - PHASES
Phase | Order
Pre-commissioning | 1
Commissioning | 2
Post-commissioning | 3
10 - PEOPLE feeds the Responsible, Approver and Owner dropdowns
Name | Role
A. Mercer | Contract Manager
S. Okonkwo | Commissioning Manager
L. Fontaine | Quality Lead
D. Petrov | Lead Commissioning Engineer
J. Whitfield | Commissioning Engineer
P. Nakamura | Commissioning Engineer
K. Rasmussen | Commissioning Engineer
R. Bellamy | Commissioning Engineer
N. Bergstrom | Commissioning Engineer
M. Haddad | Document Controller
C. Vasquez | Approver
H. Lindqvist | Approver
Formulas:
Planned date = IF([Counts as]<>"",[Counts as],IF(OR([Status code]="",[Family]="",CTR_EARLIEST=""),"",CTR_EARLIEST+[Family]))
Planned date = IF([Status code]="","",IF(COUNTIFS(EQP_SYS,[Status code],EQP_START,">0")=0,"",SUMPRODUCT(MIN((EQP_SYS=[Status code])*(EQP_START>0)*EQP_START+((EQP_SYS=[Status code])*(EQP_START>0)=0)*2958465))))
Note on C15: Earliest planned commissioning start across all equipment in section 7. Every 'Commissioning Start' anchored target date ultimately derives from the start date of whatever the document covers, not from this single figure.
Note on D71: Type a date here to override the offset calculation for that milestone.
Note on K89: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K90: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K91: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K92: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K93: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K94: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K95: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K96: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K97: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K98: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K99: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K100: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K101: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K102: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K103: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K104: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K105: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K106: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K107: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K108: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K109: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K110: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K111: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K112: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.
Note on K113: Core (ATS) deliverables that do not exist as a row for this system. Only rows carrying a gap key count: a covered slot leaves the key empty.

## HOW IT WORKS
HOW IT WORKS
This workbook does not measure progress. It measures whether deliverables are on time against the commissioning start of whatever they cover.
THE ONE RULE
Target approval date | The earliest commissioning start among what the document covers (actual if known, otherwise planned), minus the lead time of its type. Post-commissioning types are measured back from their anchor milestone instead.
Days late | Positive = late. Negative = float. One convention everywhere.
Scope | All = the whole contract. System = one system. Equipment = one item. A document covering three systems is three rows.
START HERE
1. Contract and thresholds | SETUP sections 1 and 2.
2. Systems and equipment | SETUP sections 6 and 7. The planned commissioning start you type against each equipment item is what drives every target date behind it.
3. Check the type library | SETUP section 8. Phase, anchor milestone, lead time, core (ATS) flag and default scope for each type.
4. Enter deliverables | TRACKER. Pick a Type and a Scope; the target date appears.
5. Work the lists | DASHBOARD. In progress, Missing, Coming - documents and actions together.
READING THE TRACKER
Target override | Type a date to force a target the calculation cannot know - a cross-system dependency, a site event. The Source column then reads Manual. Clear the cell to fall back to Auto.
Source | Auto = calculated. Manual = you overrode it. Nothing is ever silently overwritten.
Check | Data-quality flag: scope not set, equipment not in that system, approved with no approval date. Empty means the row is clean.
Greyed cells | Not relevant for that row's scope. System is greyed for Scope = All; Equipment is greyed unless Scope = Equipment.
STATE COLOURS
Red | Late - the target approval date has passed.
Amber | At risk - due inside the document alert window.
Blue | In progress - an actual start date is filled in.
Pale amber | Coming - not started, due inside the horizon.
Green | Done - S4A reached, a P-code published, or an approval date entered.
Grey | Inactive - cancelled, revoked, superseded, transferred, destroyed.
Orange | Needs attention: scope not resolved, no target date, type not configured, or a data-quality flag.
WHAT 'MISSING' MEANS
Missing | A deliverable flagged Core required (ATS) in the library that does not exist as a row at all for a system or an equipment item. The workbook builds the expected matrix from the library and reports the gaps, ordered by when each would have been needed.
Covered by | A system-wide or contract-wide document counts as coverage for the equipment beneath it. Inactive documents do not count as coverage.
CAPACITY AND LIMITS
Rows | TRACKER 500 rows - ACTIONS 150 - systems 25 - equipment 80 - milestones 15 - core types tracked for gaps 12.
One flat table | The TRACKER is a single table, not one block per type. Capacity is shared: 500 rows go wherever they are needed, and you can filter or sort across every type at once.
To add rows | Copy the last data row and paste down, then widen the named ranges in Formulas > Name Manager.
No macros | Formulas only. Nothing to enable, nothing a corporate policy can block.
Excel version | Uses no function newer than Excel 2007, so it runs on any current corporate build.
ASSUMPTIONS
Months to days | 30 days per month (T-3 months = 90), which reproduces the worked example in the source specification exactly.
Post-commissioning anchors | Anchored to named milestones rather than to guessed day counts. Adjust the offsets in SETUP section 5.
Equipment with no date | If nothing behind a row has a commissioning start, the row reads 'Scope not resolved' rather than inventing a target.

## LISTS (hidden)
LISTS - staging. Generated automatically; do not edit.
Basis of Commissioning | All | 360 | Commissioning Start | Contract | Whole contract | Basis of Commissioning |  | Document | DMIC-ALL-BOC-001 - Basis of Commissioning | Whole contract | S. Okonkwo | 2025-10-29 | -4 |  |  |  | Done | 42 | Open | 9 | SYS-TP | 2 | 0 | Aug 26 | 0 | Done | All | Yes
Surveillance Strategy | All | 360 | Commissioning Start | Contract | Whole contract | Surveillance Strategy |  | Document | DMIC-ALL-SVS-002 - Surveillance Strategy | Whole contract | L. Fontaine | 2025-10-29 | -3 |  |  |  | In progress | 4 | In progress | 6 | SYS-SG | 1 | 0 | Sep 26 | 2 | In progress | System | No
Surveillance Programme | System | 270 | Commissioning Start |  |  |  |  | Document | DMIC-ALL-CPE-003 - Competency Evidence | Whole contract | D. Petrov | 2026-01-27 | 210 | 210 |  | 210 | Late | 5 | On hold | 2 | SYS-TV | 1 | 0 | Oct 26 | 3 | Inactive | Equipment
Competency Evidence | All | 270 | Commissioning Start | Contract | Whole contract | Competency Evidence |  | Document | DMIC-SYS-TP-SVP-004 - Surveillance Programme | SYS-TP | J. Whitfield | 2026-01-27 | -1 |  |  |  | At risk | 0 | Done | 1 | SYS-FA | 0 | 0 | Nov 26 | 0
Safe System Of Work | System | 180 | Commissioning Start |  |  |  |  | Document | DMIC-SYS-TP-SSW-005 - Safe System Of Work | SYS-TP | P. Nakamura | 2026-09-15 | -141 |  |  |  | Coming | 0 |  |  | SYS-LV | 0 | 0 | Dec 26 | 1
Risk Assessment And Method Statement | System | 180 | Commissioning Start |  |  |  |  | Document | DMIC-SYS-TP-RAM-006 - Risk Assessment And Method Statement | SYS-TP | K. Rasmussen | 2026-04-27 | 1 |  |  |  | Not yet due | 43 |  |  | SYS-CC | 0 | 0 | Jan 27 | 9
System Commissioning Programme | System | 180 | Commissioning Start |  |  |  |  | Document | DMIC-SYS-TP-SCP-007 - System Commissioning Programme | SYS-TP | R. Bellamy | 2026-04-27 | 2 |  |  |  | Inactive | 2 |  |  |  | 0 | 0 | Feb 27 | 2
Commissioning Procedure | Equipment | 90 | Commissioning Start |  |  |  |  | Document | DMIC-SYS-TP-ATS-008 - Authority To Start Evidence | SYS-TP | N. Bergstrom | 2026-10-10 | -47 |  |  |  | No target date | 0 |  |  |  | 0 | 0 | Mar 27 | 2
Inspection and Test Plan | Equipment | 90 | Commissioning Start |  |  |  |  | Document | DMIC-SYS-SG-SVP-009 - Surveillance Programme | SYS-SG | M. Haddad | 2026-04-27 | 4 | [8 empty] | 0 | 0 | Apr 27 | 5
Planned End Of Erection Status Report | Equipment | 30 | Commissioning Start |  |  |  |  | Document | DMIC-SYS-SG-SSW-010 - Safe System Of Work | SYS-SG | C. Vasquez | 2026-07-26 | 30 | 30 |  | 30 | [5 empty] | 0 | 0 | May 27 | 3
Authority To Start Evidence | System | 14 | Commissioning Start |  |  |  |  | Document | DMIC-SYS-SG-RAM-011 - Risk Assessment And Method Statement | SYS-SG | H. Lindqvist | 2026-07-26 | -5 | [8 empty] | 0 | 0 | Jun 27 | 3
[8 empty] | Document | DMIC-SYS-SG-SCP-012 - System Commissioning Programme | SYS-SG | A. Mercer | 2026-07-26 | -4 | [8 empty] | 0 | 0 | Jul 27 | 6
[8 empty] | Document | DMIC-SYS-SG-ATS-013 - Authority To Start Evidence | SYS-SG | S. Okonkwo | 2027-01-08 | -142 | [8 empty] | 0 | 0
[8 empty] | Document | DMIC-SYS-TV-SVP-014 - Surveillance Programme | SYS-TV | L. Fontaine | 2026-07-26 | 30 | 30 |  | 30 | [5 empty] | 0 | 0
|  |  |  | System | SYS-TP | Surveillance Programme |  | Document | DMIC-SYS-TV-SSW-015 - Safe System Of Work | SYS-TV | D. Petrov | 2026-10-24 | -61 | [8 empty] | 0 | 0
[8 empty] | Document | DMIC-SYS-TV-RAM-016 - Risk Assessment And Method Statement | SYS-TV | J. Whitfield | 2026-10-24 | -60 | -60 | [7 empty] | 0 | 0
|  |  |  | System | SYS-TP | Safe System Of Work |  | Document | DMIC-SYS-TV-SCP-017 - System Commissioning Programme | SYS-TV | P. Nakamura | 2026-10-24 | -60 | -60 | [7 empty] | 0 | 0
|  |  |  | System | SYS-TP | Risk Assessment And Method Statement |  | Document | DMIC-SYS-TV-ATS-018 - Authority To Start Evidence | SYS-TV | K. Rasmussen | 2027-04-08 | -230 | [8 empty] | 0 | 0
|  |  |  | System | SYS-TP | System Commissioning Programme |  | Document | DMIC-SYS-FA-SVP-019 - Surveillance Programme | SYS-FA | R. Bellamy | 2026-10-24 | -60 | -60 | [7 empty] | 0 | 0
[8 empty] | Document | DMIC-SYS-FA-SSW-020 - Safe System Of Work | SYS-FA | N. Bergstrom | 2027-01-22 | -150 | [8 empty] | 0 | 0
[8 empty] | Document | DMIC-SYS-FA-RAM-021 - Risk Assessment And Method Statement | SYS-FA | M. Haddad | 2027-01-22 | -150 | [8 empty] | 0 | 0
[8 empty] | Document | DMIC-SYS-FA-SCP-022 - System Commissioning Programme | SYS-FA | C. Vasquez | 2027-01-22 | -150 | [8 empty] | 0 | 0
|  |  |  | System | SYS-TP | Authority To Start Evidence |  | Document | DMIC-SYS-FA-ATS-023 - Authority To Start Evidence | SYS-FA | H. Lindqvist | 2027-07-07 | -316 | [8 empty] | 0 | 0
[8 empty] | Document | DMIC-SYS-LV-SVP-024 - Surveillance Programme | SYS-LV | A. Mercer | 2027-01-22 | -150 | [8 empty] | 0 | 0
[8 empty] | Document | DMIC-SYS-LV-SSW-025 - Safe System Of Work | SYS-LV | S. Okonkwo | 2027-04-22 | -240 | [8 empty] | 0 | 0
[8 empty] | Document | DMIC-SYS-LV-RAM-026 - Risk Assessment And Method Statement | SYS-LV | L. Fontaine | 2027-04-22 | -240
|  |  |  | System | SYS-SG | Surveillance Programme |  | Document | DMIC-SYS-LV-SCP-027 - System Commissioning Programme | SYS-LV | D. Petrov | 2027-04-22 | -240
[8 empty] | Document | DMIC-SYS-CC-SVP-028 - Surveillance Programme | SYS-CC | J. Whitfield | 2027-05-02 | -250
|  |  |  | System | SYS-SG | Safe System Of Work |  | Document | DMIC-SYS-CC-SSW-029 - Safe System Of Work | SYS-CC | P. Nakamura | 2027-07-31 | -340
|  |  |  | System | SYS-SG | Risk Assessment And Method Statement |  | Document | DMIC-SYS-CC-RAM-030 - Risk Assessment And Method Statement | SYS-CC | K. Rasmussen | 2027-07-31 | -340
|  |  |  | System | SYS-SG | System Commissioning Programme |  | Document | DMIC-SYS-TP-CPR-031 - Commissioning Procedure | TP-BSS-01 Bulk Supply Substation | R. Bellamy | 2026-07-26 | 30 | 30 |  | 30
[8 empty] | Document | DMIC-SYS-TP-ITP-032 - Inspection and Test Plan | TP-BSS-01 Bulk Supply Substation | N. Bergstrom | 2026-07-26 | 5
[8 empty] | Document | DMIC-SYS-TP-PER-033 - Planned End Of Erection Status Report | TP-BSS-01 Bulk Supply Substation | M. Haddad | 2026-09-24 | -35
[8 empty] | Document | DMIC-SYS-TP-CPR-034 - Commissioning Procedure | TP-TSS-02 Traction Substation Alpha | C. Vasquez | 2026-08-15 | -4
|  |  |  | System | SYS-SG | Authority To Start Evidence |  | Document | DMIC-SYS-TP-ITP-035 - Inspection and Test Plan | TP-TSS-02 Traction Substation Alpha | H. Lindqvist | 2026-08-15 | -3
[8 empty] | Document | DMIC-SYS-TP-PER-036 - Planned End Of Erection Status Report | TP-TSS-02 Traction Substation Alpha | A. Mercer | 2026-10-14 | -51
[8 empty] | Document | DMIC-SYS-TP-CPR-037 - Commissioning Procedure | TP-TSS-03 Traction Substation Bravo | S. Okonkwo | 2026-09-04
[8 empty] | Document | DMIC-SYS-TP-ITP-038 - Inspection and Test Plan | TP-TSS-03 Traction Substation Bravo | L. Fontaine | 2026-09-04 | -10 | -10
|  |  |  | System | SYS-TV | Surveillance Programme |  | Document | DMIC-SYS-TP-PER-039 - Planned End Of Erection Status Report | TP-TSS-03 Traction Substation Bravo | D. Petrov | 2026-11-03 | -74
[8 empty] | Document | DMIC-SYS-TP-CPR-040 - Commissioning Procedure | TP-OHL-04 Overhead Line Section A | J. Whitfield | 2026-09-19 | -30
|  |  |  | System | SYS-TV | Safe System Of Work |  | Document | DMIC-SYS-TP-ITP-041 - Inspection and Test Plan | TP-OHL-04 Overhead Line Section A | P. Nakamura | 2026-09-19 | -31
|  |  |  | System | SYS-TV | Risk Assessment And Method Statement |  | Document | DMIC-SYS-TP-PER-042 - Planned End Of Erection Status Report | TP-OHL-04 Overhead Line Section A | K. Rasmussen | 2026-11-18 | -85
|  |  |  | System | SYS-TV | System Commissioning Programme |  | Document | DMIC-SYS-SG-CPR-043 - Commissioning Procedure | SG-IXL-01 Interlocking Cabinet North | R. Bellamy | 2026-10-24 | -61
[8 empty] | Document | DMIC-SYS-SG-ITP-044 - Inspection and Test Plan | SG-IXL-01 Interlocking Cabinet North | N. Bergstrom | 2026-10-24 | -62
[8 empty] | Document | DMIC-SYS-SG-PER-045 - Planned End Of Erection Status Report | SG-IXL-01 Interlocking Cabinet North | M. Haddad | 2026-12-23 | -120
[8 empty] | Document | DMIC-SYS-SG-CPR-046 - Commissioning Procedure | SG-IXL-02 Interlocking Cabinet South | C. Vasquez | 2026-11-18 | -89
|  |  |  | System | SYS-TV | Authority To Start Evidence |  | Document | DMIC-SYS-SG-ITP-047 - Inspection and Test Plan | SG-IXL-02 Interlocking Cabinet South | H. Lindqvist | 2026-11-18 | -90
[8 empty] | Document | DMIC-SYS-SG-PER-048 - Planned End Of Erection Status Report | SG-IXL-02 Interlocking Cabinet South | A. Mercer | 2027-01-17 | -151
[8 empty] | Document | DMIC-SYS-SG-CPR-049 - Commissioning Procedure | SG-ATP-03 ATP Trackside Equipment | S. Okonkwo | 2026-12-08 | -105
[8 empty] | Document | DMIC-SYS-SG-ITP-050 - Inspection and Test Plan | SG-ATP-03 ATP Trackside Equipment | L. Fontaine | 2026-12-08 | -106
|  |  |  | System | SYS-FA | Surveillance Programme |  | Document | DMIC-SYS-SG-PER-051 - Planned End Of Erection Status Report | SG-ATP-03 ATP Trackside Equipment | D. Petrov | 2027-02-06 | -167
[8 empty] | Document | DMIC-SYS-SG-CPR-052 - Commissioning Procedure | SG-OCC-04 Signalling Workstations | J. Whitfield | 2027-01-02 | -130
|  |  |  | System | SYS-FA | Safe System Of Work |  | Document | DMIC-SYS-SG-ITP-053 - Inspection and Test Plan | SG-OCC-04 Signalling Workstations | P. Nakamura | 2027-01-02 | -134
|  |  |  | System | SYS-FA | Risk Assessment And Method Statement |  | Document | DMIC-SYS-SG-PER-054 - Planned End Of Erection Status Report | SG-OCC-04 Signalling Workstations | K. Rasmussen | 2027-03-03 | -195
|  |  |  | System | SYS-FA | System Commissioning Programme |  | Document | DMIC-SYS-TV-CPR-055 - Commissioning Procedure | TV-JET-01 Jet Fan Array Tunnel 1 | R. Bellamy | 2027-01-22 | -150
[8 empty] | Document | DMIC-SYS-TV-ITP-056 - Inspection and Test Plan | TV-JET-01 Jet Fan Array Tunnel 1 | N. Bergstrom | 2027-01-22 | -150
[8 empty] | Document | DMIC-SYS-TV-PER-057 - Planned End Of Erection Status Report | TV-JET-01 Jet Fan Array Tunnel 1 | M. Haddad | 2027-03-23 | -211
[8 empty] | Document | DMIC-SYS-TV-CPR-058 - Commissioning Procedure | TV-JET-02 Jet Fan Array Tunnel 2 | C. Vasquez | 2027-02-21 | -180
|  |  |  | System | SYS-FA | Authority To Start Evidence |  | Document | DMIC-SYS-TV-ITP-059 - Inspection and Test Plan | TV-JET-02 Jet Fan Array Tunnel 2 | H. Lindqvist | 2027-02-21 | -180
[8 empty] | Document | DMIC-SYS-TV-PER-060 - Planned End Of Erection Status Report | TV-JET-02 Jet Fan Array Tunnel 2 | A. Mercer | 2027-04-22 | -244
[8 empty] | Document | DMIC-SYS-TV-CPR-061 - Commissioning Procedure | TV-SMK-03 Smoke Extraction Plant | S. Okonkwo | 2027-03-23 | -210
[8 empty] | Document | DMIC-SYS-TV-ITP-062 - Inspection and Test Plan | TV-SMK-03 Smoke Extraction Plant | L. Fontaine | 2027-03-23 | -210
|  |  |  | System | SYS-LV | Surveillance Programme |  | Document | DMIC-SYS-TV-PER-063 - Planned End Of Erection Status Report | TV-SMK-03 Smoke Extraction Plant | D. Petrov | 2027-05-22 | -270
[8 empty] | Document | DMIC-SYS-FA-CPR-064 - Commissioning Procedure | FA-PAN-01 Fire Panel Main | J. Whitfield | 2027-04-22 | -240
|  |  |  | System | SYS-LV | Safe System Of Work |  | Document | DMIC-SYS-FA-ITP-065 - Inspection and Test Plan | FA-PAN-01 Fire Panel Main | P. Nakamura | 2027-04-22 | -240
|  |  |  | System | SYS-LV | Risk Assessment And Method Statement |  | Document | DMIC-SYS-FA-PER-066 - Planned End Of Erection Status Report | FA-PAN-01 Fire Panel Main | K. Rasmussen | 2027-06-21 | -300
|  |  |  | System | SYS-LV | System Commissioning Programme |  | Document | DMIC-SYS-FA-CPR-067 - Commissioning Procedure | FA-DET-02 Detection Loop Zone A | R. Bellamy | 2027-05-22 | -270
[8 empty] | Document | DMIC-SYS-FA-ITP-068 - Inspection and Test Plan | FA-DET-02 Detection Loop Zone A | N. Bergstrom | 2027-05-22 | -270
[8 empty] | Document | DMIC-SYS-FA-PER-069 - Planned End Of Erection Status Report | FA-DET-02 Detection Loop Zone A | M. Haddad | 2027-07-21 | -330
[8 empty] | Document | DMIC-SYS-FA-CPR-070 - Commissioning Procedure | FA-SUP-03 Suppression Skid | C. Vasquez | 2027-06-16 | -295
|  |  |  | System | SYS-LV | Authority To Start Evidence | 2027-10-05 | Document | DMIC-SYS-FA-ITP-071 - Inspection and Test Plan | FA-SUP-03 Suppression Skid | H. Lindqvist | 2027-06-16 | -295
[8 empty] | Document | DMIC-SYS-LV-CPR-072 - Commissioning Procedure | LV-SWB-01 Main LV Switchboard | A. Mercer | 2027-07-21 | -330
[8 empty] | Document | DMIC-SYS-LV-ITP-073 - Inspection and Test Plan | LV-SWB-01 Main LV Switchboard | S. Okonkwo | 2027-07-21 | -330
[8 empty] | Document | DMIC-SYS-LV-PER-074 - Planned End Of Erection Status Report | LV-SWB-01 Main LV Switchboard | L. Fontaine | 2027-09-19
|  |  |  | System | SYS-CC | Surveillance Programme |  | Document | DMIC-SYS-LV-CPR-075 - Commissioning Procedure | LV-UPS-02 UPS Room A | D. Petrov | 2027-08-25 | -365
[8 empty] | Document | DMIC-SYS-LV-ITP-076 - Inspection and Test Plan | LV-UPS-02 UPS Room A | J. Whitfield | 2027-08-25 | -365
|  |  |  | System | SYS-CC | Safe System Of Work |  | Document | DMIC-SYS-LV-PER-077 - Planned End Of Erection Status Report | LV-UPS-02 UPS Room A | P. Nakamura | 2027-10-24 | -425
|  |  |  | System | SYS-CC | Risk Assessment And Method Statement |  | Document | DMIC-SYS-LV-CPR-078 - Commissioning Procedure | LV-GEN-03 Standby Generator | K. Rasmussen | 2027-09-24 | -395
|  |  |  | System | SYS-CC | System Commissioning Programme | 2027-07-31 | Document | DMIC-SYS-LV-PER-079 - Planned End Of Erection Status Report | LV-GEN-03 Standby Generator | R. Bellamy | 2027-11-23 | -455
[8 empty] | Document | DMIC-SYS-CC-CPR-080 - Commissioning Procedure | CC-SRV-01 SCADA Server Cluster | N. Bergstrom | 2027-10-29 | -430
[8 empty] | Document | DMIC-SYS-CC-ITP-081 - Inspection and Test Plan | CC-SRV-01 SCADA Server Cluster | M. Haddad | 2027-10-29 | -430
[8 empty] | Document | DMIC-SYS-CC-PER-082 - Planned End Of Erection Status Report | CC-SRV-01 SCADA Server Cluster | C. Vasquez | 2027-12-28 | -490
|  |  |  | System | SYS-CC | Authority To Start Evidence | 2028-01-13 | Document | DMIC-SYS-CC-ITP-083 - Inspection and Test Plan | CC-HMI-02 Operator Workstations | H. Lindqvist | 2027-11-28 | -460
[8 empty] | Document | DMIC-SYS-CC-PER-084 - Planned End Of Erection Status Report | CC-HMI-02 Operator Workstations | A. Mercer | 2028-01-27 | -520
[8 empty] | Document | DMIC-SYS-CC-ITP-085 - Inspection and Test Plan | CC-NET-03 Control Network Core | S. Okonkwo | 2027-12-23 | -485
[8 empty] | Document | DMIC-SYS-CC-PER-086 - Planned End Of Erection Status Report | CC-NET-03 Control Network Core | L. Fontaine | 2028-02-21 | -545
[8 empty] | Document | DMIC-SYS-TP-IER-087 - Initial End Of Erection Status Report | TP-BSS-01 Bulk Supply Substation | D. Petrov | 2026-07-26 | 30 | 30.0001 |  | 30.0001
[8 empty] | Document | DMIC-SYS-TP-IER-088 - Initial End Of Erection Status Report | TP-TSS-02 Traction Substation Alpha | J. Whitfield | 2026-08-15 | -5
[8 empty] | Document | DMIC-SYS-TP-IER-089 - Initial End Of Erection Status Report | TP-TSS-03 Traction Substation Bravo | P. Nakamura | 2026-09-04 | -15
[8 empty] | Document | DMIC-SYS-TP-IER-090 - Initial End Of Erection Status Report | TP-OHL-04 Overhead Line Section A | K. Rasmussen | 2026-09-19 | -31
[8 empty] | Document | DMIC-SYS-SG-IER-091 - Initial End Of Erection Status Report | SG-IXL-01 Interlocking Cabinet North | R. Bellamy | 2026-10-24 | -60
[8 empty] | Document | DMIC-SYS-SG-IER-092 - Initial End Of Erection Status Report | SG-IXL-02 Interlocking Cabinet South | N. Bergstrom | 2026-11-18 | -86
[8 empty] | Document | DMIC-SYS-SG-IER-093 - Initial End Of Erection Status Report | SG-ATP-03 ATP Trackside Equipment | M. Haddad | 2026-12-08 | -107
[8 empty] | Document | DMIC-SYS-SG-IER-094 - Initial End Of Erection Status Report | SG-OCC-04 Signalling Workstations | C. Vasquez | 2027-01-02 | -130
[8 empty] | Document | DMIC-SYS-TV-IER-095 - Initial End Of Erection Status Report | TV-JET-01 Jet Fan Array Tunnel 1 | H. Lindqvist | 2027-01-22 | -150
[8 empty] | Document | DMIC-SYS-TV-IER-096 - Initial End Of Erection Status Report | TV-JET-02 Jet Fan Array Tunnel 2 | A. Mercer | 2027-02-21 | -185
|  |  |  | Equipment | TP-BSS-01 Bulk Supply Substation | Commissioning Procedure
|  |  |  | Equipment | TP-BSS-01 Bulk Supply Substation | Inspection and Test Plan
|  |  |  | Equipment | TP-BSS-01 Bulk Supply Substation | Planned End Of Erection Status Report
|  |  |  | Equipment | TP-TSS-02 Traction Substation Alpha | Commissioning Procedure
|  |  |  | Equipment | TP-TSS-02 Traction Substation Alpha | Inspection and Test Plan
|  |  |  | Equipment | TP-TSS-02 Traction Substation Alpha | Planned End Of Erection Status Report
|  |  |  | Equipment | TP-TSS-03 Traction Substation Bravo | Commissioning Procedure | 2026-09-04
|  |  |  | Equipment | TP-TSS-03 Traction Substation Bravo | Inspection and Test Plan
|  |  |  | Equipment | TP-TSS-03 Traction Substation Bravo | Planned End Of Erection Status Report
|  |  |  | Equipment | TP-OHL-04 Overhead Line Section A | Commissioning Procedure
|  |  |  | Equipment | TP-OHL-04 Overhead Line Section A | Inspection and Test Plan
|  |  |  | Equipment | TP-OHL-04 Overhead Line Section A | Planned End Of Erection Status Report
|  |  |  | Equipment | SG-IXL-01 Interlocking Cabinet North | Commissioning Procedure
|  |  |  | Equipment | SG-IXL-01 Interlocking Cabinet North | Inspection and Test Plan
|  |  |  | Equipment | SG-IXL-01 Interlocking Cabinet North | Planned End Of Erection Status Report
|  |  |  | Equipment | SG-IXL-02 Interlocking Cabinet South | Commissioning Procedure
|  |  |  | Equipment | SG-IXL-02 Interlocking Cabinet South | Inspection and Test Plan
|  |  |  | Equipment | SG-IXL-02 Interlocking Cabinet South | Planned End Of Erection Status Report
|  |  |  | Equipment | SG-ATP-03 ATP Trackside Equipment | Commissioning Procedure
|  |  |  | Equipment | SG-ATP-03 ATP Trackside Equipment | Inspection and Test Plan
|  |  |  | Equipment | SG-ATP-03 ATP Trackside Equipment | Planned End Of Erection Status Report
|  |  |  | Equipment | SG-OCC-04 Signalling Workstations | Commissioning Procedure
|  |  |  | Equipment | SG-OCC-04 Signalling Workstations | Inspection and Test Plan
|  |  |  | Equipment | SG-OCC-04 Signalling Workstations | Planned End Of Erection Status Report
|  |  |  | Equipment | TV-JET-01 Jet Fan Array Tunnel 1 | Commissioning Procedure
|  |  |  | Equipment | TV-JET-01 Jet Fan Array Tunnel 1 | Inspection and Test Plan
|  |  |  | Equipment | TV-JET-01 Jet Fan Array Tunnel 1 | Planned End Of Erection Status Report
|  |  |  | Equipment | TV-JET-02 Jet Fan Array Tunnel 2 | Commissioning Procedure
|  |  |  | Equipment | TV-JET-02 Jet Fan Array Tunnel 2 | Inspection and Test Plan
|  |  |  | Equipment | TV-JET-02 Jet Fan Array Tunnel 2 | Planned End Of Erection Status Report
|  |  |  | Equipment | TV-SMK-03 Smoke Extraction Plant | Commissioning Procedure
|  |  |  | Equipment | TV-SMK-03 Smoke Extraction Plant | Inspection and Test Plan
|  |  |  | Equipment | TV-SMK-03 Smoke Extraction Plant | Planned End Of Erection Status Report
|  |  |  | Equipment | FA-PAN-01 Fire Panel Main | Commissioning Procedure
|  |  |  | Equipment | FA-PAN-01 Fire Panel Main | Inspection and Test Plan
|  |  |  | Equipment | FA-PAN-01 Fire Panel Main | Planned End Of Erection Status Report
|  |  |  | Equipment | FA-DET-02 Detection Loop Zone A | Commissioning Procedure
|  |  |  | Equipment | FA-DET-02 Detection Loop Zone A | Inspection and Test Plan
|  |  |  | Equipment | FA-DET-02 Detection Loop Zone A | Planned End Of Erection Status Report
|  |  |  | Equipment | FA-SUP-03 Suppression Skid | Commissioning Procedure
|  |  |  | Equipment | FA-SUP-03 Suppression Skid | Inspection and Test Plan
|  |  |  | Equipment | FA-SUP-03 Suppression Skid | Planned End Of Erection Status Report | 2027-08-15 00:01
|  |  |  | Equipment | LV-SWB-01 Main LV Switchboard | Commissioning Procedure
|  |  |  | Equipment | LV-SWB-01 Main LV Switchboard | Inspection and Test Plan
|  |  |  | Equipment | LV-SWB-01 Main LV Switchboard | Planned End Of Erection Status Report | 2027-09-19 00:01
|  |  |  | Equipment | LV-UPS-02 UPS Room A | Commissioning Procedure
|  |  |  | Equipment | LV-UPS-02 UPS Room A | Inspection and Test Plan |  | Action | ACT-001 - Close out RAMS comments raised by the Client safety review | SYS-SG | D. Petrov | 2026-08-03 | 22 | 22 |  | 22
|  |  |  | Equipment | LV-UPS-02 UPS Room A | Planned End Of Erection Status Report |  | Action | ACT-002 - Obtain signed competency records for the ATP trackside team | SG-ATP-03 ATP Trackside Equipment | J. Whitfield | 2026-08-13 | 12 | 12 |  | 12
[8 empty] | Action | ACT-003 - Resolve interlocking cabinet earthing non-conformance | SG-IXL-01 Interlocking Cabinet North | P. Nakamura | 2026-08-20 | 5 | 5 |  | 5
[8 empty] | Action | ACT-004 - Issue System Commissioning Programme revision C for approval | SYS-TV | K. Rasmussen | 2026-08-27 | -2 |  | -2
[8 empty] | Action | ACT-005 - Agree tunnel ventilation witnessing schedule with the Author | SYS-TV | R. Bellamy | 2026-09-03 | -9 |  | -9
[8 empty] | Action | ACT-006 - Confirm 33kV protection settings against the final study | TP-TSS-03 Traction Substation Bravo | N. Bergstrom | 2026-09-10 | -16 | -16
[8 empty] | Action | ACT-007 - Update Basis of Commissioning for the revised staging strate | - | M. Haddad | 2026-09-18 | -24 |  | -24
[8 empty] | Action | ACT-008 - Mobilise second commissioning engineer for tunnel ventilatio | SYS-TV | C. Vasquez | 2026-09-25 | -31 |  | -31
[8 empty] | Action | ACT-009 - Close punch list items on Traction Substation Alpha | TP-TSS-02 Traction Substation Alpha | H. Lindqvist | 2026-09-06 | -12 | -12
[8 empty] | Action | ACT-010 - Submit Initial EESR for the signalling scope | SYS-SG | A. Mercer | 2026-08-22 | 3 | 3 |  | 3
[8 empty] | Action | ACT-011 - Agree beneficial use conditions with Operations | SYS-TP | S. Okonkwo | 2026-10-08 | -44 |  | -44
|  |  |  | Equipment | LV-GEN-03 Standby Generator | Commissioning Procedure |  | Action | ACT-012 - Verify smoke extraction damper actuator supply | TV-SMK-03 Smoke Extraction Plant | L. Fontaine | 2026-10-15 | -51 |  | -51
|  |  |  | Equipment | LV-GEN-03 Standby Generator | Inspection and Test Plan | 2027-09-24 00:01 | Action | ACT-013 - Complete fire detection loop cause and effect matrix | FA-DET-02 Detection Loop Zone A | D. Petrov | 2026-10-24 | -60 |  | -60
|  |  |  | Equipment | LV-GEN-03 Standby Generator | Planned End Of Erection Status Report |  | Action | ACT-014 - Rectify jet fan vibration readings on Tunnel 1 | TV-JET-01 Jet Fan Array Tunnel 1 | J. Whitfield | 2026-08-24 | 1 | 1 |  | 1
[8 empty] | Action | ACT-015 - Archive approved bulk supply substation records | TP-BSS-01 Bulk Supply Substation | P. Nakamura | 2026-07-26 | -2
[8 empty] | Action | ACT-016 - Confirm SCADA point list against the signalling interface | CC-SRV-01 SCADA Server Cluster | K. Rasmussen | 2026-11-08 | -75 |  | -75
[8 empty] | Action | ACT-017 - Book UPS discharge test window with Operations | LV-UPS-02 UPS Room A | R. Bellamy | 2026-11-01 | -68 |  | -68
[8 empty] | Action | ACT-018 - Issue Authority To Start evidence pack for traction power | SYS-TP | N. Bergstrom | 2026-08-31 | -6 | -6
|  |  |  | Equipment | CC-SRV-01 SCADA Server Cluster | Commissioning Procedure
|  |  |  | Equipment | CC-SRV-01 SCADA Server Cluster | Inspection and Test Plan
|  |  |  | Equipment | CC-SRV-01 SCADA Server Cluster | Planned End Of Erection Status Report
|  |  |  | Equipment | CC-HMI-02 Operator Workstations | Commissioning Procedure | 2027-11-28 00:01
|  |  |  | Equipment | CC-HMI-02 Operator Workstations | Inspection and Test Plan
|  |  |  | Equipment | CC-HMI-02 Operator Workstations | Planned End Of Erection Status Report
|  |  |  | Equipment | CC-NET-03 Control Network Core | Commissioning Procedure | 2027-12-23 00:01
|  |  |  | Equipment | CC-NET-03 Control Network Core | Inspection and Test Plan
|  |  |  | Equipment | CC-NET-03 Control Network Core | Planned End Of Erection Status Report