## 01_Meeting_Tracker
Meeting Tracker | Action Log | Meeting History | Meeting Summary | Lists Config
Meeting Tracker
One row per recurring topic. Shows the latest position only - full history is in Meeting History. Sort or filter by Status to prepare the next meeting: Action Required, then To Discuss, then Monitoring, then Closed.
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ New row: type directly below the table and Excel extends it automatically |  |  | Overdue Actions: |  |  | Topics to Discuss:
Identification |  |  | Position |  | Action |  |  | Status & Review |  |  | Reference | Helper
Topic ID | Category | Topic | Latest Position | What Needs Attention? | Current Action | Owner | Due Date | Status | Last Update Date | Discuss Next Meeting? | PQCP Ref. | Priority
| Technical | Example topic - ventilation system commissioning strategy | Draft strategy issued for internal review. | Confirm the temporary supply date with Contractor A. | Contractor A to issue an updated programme. | Person A | 2026-07-15 | Action Required |  | Yes | 8.1

## 02_Action_Log
Meeting Tracker | Action Log | Meeting History | Meeting Summary | Lists Config
Action Log
Every action raised at a meeting. Closed actions stay in the table for traceability - never delete a row.
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ New row: type directly below the table and Excel extends it automatically
Identification |  |  | Detail |  | Dates & Status |  |  | Tracking |  | Helper
Action ID | Topic ID | Topic | Action | Owner | Date Raised | Due Date | Status | Latest Update | Closure Date | Overdue?
| T001 |  | Contractor A to issue an updated programme confirming the temporary supply date. | Person A | 2026-06-02 | 2026-07-15 | In Progress | Contractor A confirmed the programme is being finalised.
Formulas:
Helper = IF([Meeting Summary]="","",IF(AND([Status]<>"Closed",[Due Date]<>"",[Due Date]<TODAY()),"Yes","No"))

## 03_Meeting_History
Meeting Tracker | Action Log | Meeting History | Meeting Summary | Lists Config
Meeting History
One row per meeting update. Add a new row every month - this is the permanent record. The Meeting Tracker only ever shows the current position, not this full trail.
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ New row: type directly below the table and Excel extends it automatically
Identification |  |  | Content |  | Action Raised
Meeting Date | Topic ID | Topic | Update / Discussion | Decision | Action Raised | Owner | Due Date
2026-06-02 | T001 |  | Contractor A confirmed the temporary supply date is still to be finalised. |  | Contractor A to issue an updated programme. | Person A | 2026-07-15

## 04_Meeting_Summary
Meeting Tracker | Action Log | Meeting History | Meeting Summary | Lists Config
Meeting Summary
Fill in the meeting date and attendees. Every section below fills in automatically for that date - short enough to paste straight into minutes or an email.
Meeting Date: | 2026-06-02 |  | Attendees: | Person A, Person B
KEY UPDATES
Topic | Update
DECISIONS
Topic | Decision
ACTIONS
Action | Owner | Due Date
CLOSED ACTIONS
Action | Owner
ITEMS FOR NEXT MEETING
Topic | What Needs Attention?
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ New row: type directly below the table and Excel extends it automatically

## 05_Lists_Config
Meeting Tracker | Action Log | Meeting History | Meeting Summary | Lists Config
Lists & Configuration
Dropdown lists used across the workbook. Edit these to match your project's vocabulary - every dropdown updates automatically.
Category | Topic Status | Action Status | Yes/No
Schedule | Action Required | Open | Yes
Documentation | To Discuss | In Progress | No
Technical | Monitoring | Waiting
Resources | Closed | Closed
Safety
Quality
Other
Legend: Blue = fill in yourself ¦ Black = automatic, do not overtype ¦ New row: type directly below the table and Excel extends it automatically