## Read Me
DMIC COMMISSIONING CONTRACT MANAGEMENT WORKBOOK
Built to the specification 'DMIC Commissioning Contract Management Workbook v3'. BLANK TEMPLATE — row 4 of each tracker holds an example; overwrite it with your first real record.
START HERE
1. Set the driver date | Control Panel → 'Planned Commissioning Start' (amber cell). Every target date in the workbook is generated from it.
2. Tune the lead times | Control Panel → 'Lead Time Configuration'. Edit the blue Lead Days column; all target dates update.
3. Enter your scopes | Scope Tracker → one row per commissioning scope. The Scope ID is the key everything else links to.
4. Enter your equipment | Equipment Tracker → one row per item, each with a Parent Scope and a Commissioning Phase.
5. Enter your deliverables | Document Tracker → one row per deliverable. Pick a Document Type and the target dates appear.
6. Work the actions | Action Tracker → rows colour themselves by priority and lateness.
7. Read the Dashboard | Dashboard → Contract Health Index, the nine executive questions, milestones and nine charts.
CELL COLOUR LEGEND
Amber cell | The single key driver — Planned Commissioning Start.
Blue text, white cell | Your input. Type here.
Grey cell | Calculated. Do not type over it — you would break the roll-up.
DOCUMENT COLOUR CODING (spec)
Grey | Not Started
Blue | Draft
Yellow | Internal Review / Submitted / Under Review / Resubmitted
Orange | Comments Received
Red | Rework (rejected) — and any overdue row
Green | Approved / Released / Implemented
Dark Green | Closed
ACTION COLOUR RULES (spec)
Dark Red | Critical and overdue
Red | Overdue
Amber | Due within 14 days
Blue | In Progress
Green | Closed
Grey | Waiting
HOW READINESS IS CALCULATED
Equipment Readiness | 50% x phase progress + 50% x share of that item's linked documents approved. Equipment with no linked documents uses phase progress alone. Weights: Configuration sheet.
Scope Readiness | Average equipment readiness across the scope's equipment.
Contract Readiness | Average equipment readiness across all equipment.
Contract Health Index | 40% Documents + 20% Readiness + 15% Actions + 10% Milestones + 10% Equipment Progress + 5% Handovers. Weights: Configuration sheet.
ATS Readiness | Share of the 10 spec-mandated deliverables that are fully satisfied — the type exists in the tracker AND none of that type is still outstanding. 100% = Ready, 80%+ = At Risk, below = Not Ready.
ASSUMPTIONS WE HAD TO MAKE
Phase progress ramp | The spec names 11 commissioning phases but gives no % for each. Seeded 0% → 100%; retune on the Configuration sheet.
Months → days | Converted at 30 days per month (T-3 Months = 90), which reproduces the spec's own worked example exactly.
Post-commissioning lead times | 'During Commissioning', 'Before FTC/TFM/TFTO' and 'Before Final Takeover' have no stated duration. Seeded as T+30 to T+120 days.
'Missing Documents' | Counted as deliverables that exist as a row but are still 'Not Started'. The workbook cannot count a row you never created.
'Open Risks' | The spec defines no Risk sheet. Counted as open actions flagged as a Commissioning Blocker.
Authority To Start Evidence | Added as a 20th document type. The spec lists 19 mandatory types but the ATS gate and the Control Panel lead-time list both require it.
Readiness Trend | Excel keeps no history. Record a monthly snapshot in the Readiness Trend log on the Dashboard; the trend chart plots it.
CAPACITY & EXTENDING
Row capacity | Scope 100 rows · Equipment 100 · Documents 150 · Actions 100 · Milestones 30.
To add more rows | Select the last data row, copy it, and paste into the rows below. Then widen the named ranges (Formulas → Name Manager) so the roll-ups see the new rows.
Hidden columns | Each tracker has hidden helper columns to the right of the visible ones. They feed the dashboard and charts. Leave them alone.
Hidden sheet | 'Configuration' holds the dropdown lists, progress maps, weights and chart data. Right-click any tab → Unhide to reach it.
Generated | 20-Aug-2026 from DMIC_COMMISSIONING_CONTRACT_MANAGEMENT_WORKBOOK_v3.docx

## Control Panel
DMIC COMMISSIONING CONTRACT — CONTROL PANEL
Master page. Blue cells are for you to type in; grey cells calculate themselves. The amber cell (Planned Commissioning Start) drives every target date in the workbook.
CONTRACT INFORMATION |  |  |  | CONTRACT READINESS SUMMARY
Contract Name |  |  |  | Overall Contract Readiness % | 22.5%
Contract Manager |  |  |  | Number of Scopes | 1
Project Manager |  |  |  | Number of Equipment Items | 1
Commissioning Manager |  |  |  | Open Actions | 1
Lead Commissioning Engineer |  |  |  | Overdue Actions | 0
Quality Lead |  |  |  | Missing Documents | 0
Contract Status |  |  |  | Open Risks | 1
|  |  |  | Upcoming Milestones | 0
COMMISSIONING DATES
Planned Commissioning Start | 2027-06-01 | ◀ drives all target dates |  | RAG STATUS
Planned Commissioning Finish |  |  |  | Contract Health Index | 56%
Forecast Commissioning Start |  |  |  | Health Category | Attention Required
Forecast Commissioning Finish |  |  |  | RAG | AMBER
Actual Commissioning Start
Actual Commissioning Finish |  |  |  | AUTHORITY TO START (ATS) READINESS GATE
|  |  |  | ATS Readiness Score | 0%
SCHEDULE PERFORMANCE |  |  |  | ATS Status | Not Ready
Delay vs Baseline (days) |  |  |  | Required Types Met | 0 of 10
Days To Commissioning Start | 285 |  |  | 'Ready' requires all 10 minimum deliverable types fully approved.
LEGEND
Amber cell | The single key driver — Planned Commissioning Start.
Blue text on white | Type here. These are your inputs.
Grey cell | Calculated automatically — do not type over it.
LEAD TIME CONFIGURATION — DOCUMENTS
Target dates are generated as: Planned Commissioning Start − Lead Days. Edit the blue Lead Days column and every target date in the Document Tracker updates. A negative Lead Day value places the target AFTER commissioning start.
Document Type | Spec Lead Time | Lead Days (T minus) | Target Submission | Target Approval
Basis of Commissioning | T-12 Months | 360 | 2026-05-16 | 2026-06-06
Surveillance Strategy | T-12 Months | 360 | 2026-05-16 | 2026-06-06
Surveillance Programme | T-9 Months | 270 | 2026-08-14 | 2026-09-04
Competency Evidence | T-9 Months | 270 | 2026-08-14 | 2026-09-04
Safe System Of Work | T-6 Months | 180 | 2026-11-12 | 2026-12-03
Risk Assessment And Method Statement | T-6 Months | 180 | 2026-11-12 | 2026-12-03
System Commissioning Programme | T-6 Months | 180 | 2026-11-12 | 2026-12-03
Commissioning Procedure | T-3 Months | 90 | 2027-02-10 | 2027-03-03
Inspection and Test Plan | T-3 Months | 90 | 2027-02-10 | 2027-03-03
Initial End Of Erection Status Report | T-3 Months | 90 | 2027-02-10 | 2027-03-03
Planned End Of Erection Status Report | T-1 Month | 30 | 2027-04-11 | 2027-05-02
Authority To Start Evidence | T-2 Weeks | 14 | 2027-04-27 | 2027-05-18
Commissioning Results Sheet | During Commissioning | -30 | 2027-06-10 | 2027-07-01
Commissioning Phase Report | Commissioning Completion | -60 | 2027-07-10 | 2027-07-31
Handover Certificate | Before FTC | -75 | 2027-07-25 | 2027-08-15
Functional Takeover Package | Before FTC | -75 | 2027-07-25 | 2027-08-15
Care And Maintenance Plan | Before TFM (assumed) | -90 | 2027-08-09 | 2027-08-30
Maintenance Transfer Package | Before TFM | -90 | 2027-08-09 | 2027-08-30
Temporary Operations Transfer Package | Before TFTO | -105 | 2027-08-24 | 2027-09-14
Final End Of Erection Status Report | Before Final Takeover | -120 | 2027-09-08 | 2027-09-29
Months are converted at 30 days each: T-12 Months = 360, T-9 = 270, T-6 = 180, T-3 = 90, T-1 Month = 30, T-2 Weeks = 14. This reproduces the worked example in the specification exactly (Planned Start 01-Jan-2028, Commissioning Procedure lead 90 days → Target Approval 03-Oct-2027). The spec's post-commissioning deliverables (During Commissioning, Before FTC/TFM/TFTO, Before Final Takeover) have no stated duration and are seeded as T+30 to T+120; adjust to your programme. Source: DMIC Commissioning Contract Management Workbook v3, 'Default Lead Times' table and 'Automatic Document Deadline Calculation' example.
LEAD TIME CONFIGURATION — MILESTONES
Milestone | Spec Reference | Lead Days (T minus) | Target Date
Kick Off Meeting | Milestone Tracker | 360 | 2026-06-06
Commissioning Readiness Review | Milestone Tracker | 60 | 2027-04-02
Authority To Start | Milestone Tracker | 14 | 2027-05-18
Commissioning Start | Milestone Tracker | 0 | 2027-06-01
Functional Takeover | Milestone Tracker | -75 | 2027-08-15
Beneficial Use | Milestone Tracker | -85 | 2027-08-25
Maintenance Transfer | Milestone Tracker | -100 | 2027-09-09
Temporary Operations Transfer | Milestone Tracker | -115 | 2027-09-24
Final Takeover | Milestone Tracker | -130 | 2027-10-09
Assumption: only Kick Off (T-12M), Authority To Start (T-2W) and Commissioning Start (T) are given in the spec. The remaining milestone offsets are seeded estimates — adjust them.
Formulas:
Target Submission = IF([Target Approval]="","",[Target Approval]-Cfg_ReviewDays)
Target Submission = IF(OR(C14="",[Lead Days (T minus)]=""),"",C14-[Lead Days (T minus)])
Target Approval = IF(OR(C14="",[Lead Days (T minus)]=""),"",C14-[Lead Days (T minus)])
Note on C22: Forecast Commissioning Start minus Planned Commissioning Start. Positive = late against baseline.
Note on G5: Average blended readiness across every equipment item (phase progress + approved documents).
Note on G9: Actions past their Due Date with no Completion Date and status not Closed.
Note on G10: Assumption: the spec does not define 'missing'. Counted here as deliverables that exist as a row but whose Workflow Status is still 'Not Started'.
Note on G11: Assumption: the spec has no separate Risk sheet. Counted here as open actions flagged as a Commissioning Blocker.
Note on G12: Milestones whose forecast (or planned) date falls within the window set on the Configuration sheet, and which are not yet Achieved.

## Scope Tracker
SCOPE TRACKER
One row per Commissioning Scope. White columns are inputs; grey columns roll up automatically from the Equipment, Document and Action trackers.
Scope ID | Scope Name | Scope Owner | Planned Start | Planned Finish | Forecast Start | Forecast Finish | Actual Start | Actual Finish | Readiness % | Status | Number of Equipment | Equipment Complete | Equipment In Progress | Equipment Not Started | Open Actions | Outstanding Documents | Comments
SC-01 | Traction Power & 33kV Distribution | A. Mercer | 2026-11-03 | 2027-09-29 | 2026-11-10 | 2027-10-06 |  |  | 22.5% | In Progress | 1 | 0 | 1 | 0 | 1 | 1 | ◀ EXAMPLE ROW — overwrite with your own data

## Equipment Tracker
EQUIPMENT TRACKER
One row per Equipment Item. Each item progresses independently; Scope and Contract readiness roll up from here.
Equipment Name | Parent Scope | Responsible Engineer | Commissioning Phase | Planned Start | Forecast Start | Actual Start | Planned Finish | Forecast Finish | Actual Finish | Readiness % | Status | Comments | Linked Docs | Phase % | Doc %
TR-TSS-02 Traction Substation Alpha | SC-01 | D. Petrov | Testing In Progress | 2026-12-03 | 2026-12-08 |  | 2027-02-16 | 2027-02-23 |  | 22.5% | In Progress | ◀ EXAMPLE ROW — overwrite with your own data | 1 | 45% | 0%
Formulas:
Status = IF([Equipment Name]="","",IF([Readiness %]>=1,"Complete",IF([Readiness %]<=0,"Not Started",IF(AND([Planned Finish]<>"",[Planned Finish]<TODAY(),[Actual Finish]=""),"Behind Schedule","In Progress"))))
Note on K3: Blended readiness: (phase weight x phase progress) + (document weight x share of linked documents approved). Weights are on the Configuration sheet. Equipment with no linked documents falls back to phase progress alone.

## Document Tracker
DOCUMENT TRACKER
Primary operational sheet — one row per commissioning deliverable. Target dates are generated from the Planned Commissioning Start Date and the lead times on the Control Panel.
Document Type | Scope | Equipment (optional) | Document Number | Document Title | Revision | Owner | Reviewer | Workflow Status | Readiness Gate | Target Submission Date | Target Approval Date | Actual Submission Date | Actual Approval Date | Days Late | Criticality | Comments | Approved | Progress % | Days Remaining | Flag | Rank Key
System Commissioning Programme | SC-01 | TR-TSS-02 Traction Substation Alpha | DMIC-SC-01-SCP-001 | Traction Power — System Commissioning Programme | B | D. Petrov | M. Haddad | Under Review | Readiness | 2026-11-12 | 2026-12-03 |  |  | 0 | Critical | ◀ EXAMPLE ROW — overwrite with your own data | 0 | 55% | 105 | On Track
Formulas:
Target Submission Date = IF([Target Approval Date]="","",[Target Approval Date]-Cfg_ReviewDays)
Target Approval Date = IF([Document Type]="","",IFERROR(Ctrl_PlannedStart-INDEX(Cfg_LeadDays,MATCH([Document Type],Cfg_LeadType,0)),""))
Days Late = IF([Document Type]="","",IF([Actual Approval Date]<>"",MAX(0,[Actual Approval Date]-[Target Approval Date]),IF(AND([Target Approval Date]<>"",TODAY()>[Target Approval Date]),TODAY()-[Target Approval Date],0)))
Days Remaining = IF(OR([Document Type]="",[Target Approval Date]=""),"",[Target Approval Date]-TODAY())
Flag = IF([Document Type]="","",IF([Approved]=1,"Approved",IF(AND([Target Approval Date]<>"",TODAY()>[Target Approval Date]),"Overdue",IF(AND([Target Approval Date]<>"",[Target Approval Date]-TODAY()<=Cfg_DocWindow),"Due Soon",IF([Workflow Status]="Not Started","Not Started","On Track")))))
Note on O3: Days late against the Target Approval Date. Once an Actual Approval Date is entered it freezes at how late the approval actually was.

## Action Tracker
ACTION TRACKER
One row per Action. Rows colour themselves by priority and lateness — see the Read Me sheet for the colour key.
Action ID | Action Description | Category | Linked Scope | Linked Equipment | Linked Document | Owner | Support Owner | Date Raised | Due Date | Completion Date | Priority | Commissioning Blocker | Status | Comments | Days To Due | Overdue | Rank Key
ACT-001 | Close out RAMS comments raised by the Client safety review | Safety | SC-01 | TR-TSS-02 Traction Substation Alpha | DMIC-SC-01-SCP-001 | A. Mercer | M. Haddad | 2026-08-06 | 2026-08-27 |  | High | Yes | Open | ◀ EXAMPLE ROW — overwrite with your own data | 7 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Days To Due = IF([Action ID]="","",IF(OR([Completion Date]<>"",[Due Date]=""),"",[Due Date]-TODAY()))
Overdue = IF([Action ID]="",0,IF(AND([Status]<>"Closed",[Completion Date]="",[Due Date]<>"",[Due Date]<TODAY()),1,0))
Rank Key = IF([Action ID]="","",IF([Overdue]=1,(TODAY()-[Due Date])+ROW()/1000000,""))

## Dashboard
EXECUTIVE DASHBOARD & MILESTONES
Everything on this sheet is calculated. Nothing here needs typing except the Milestone Tracker and the Readiness Trend log.
CONTRACT HEALTH INDEX
56% |  |  |  | Health Category | Attention Required |  | Component | Score | Weight | Weighted
|  |  |  | RAG Status | AMBER |  | Documents | 55% | 40% | 22%
|  |  |  | Contract Readiness | 22.5% |  | Readiness | 22.5% | 20% | 4.5%
|  |  |  | ATS Readiness | 0% |  | Actions | 100% | 15% | 15%
[7 empty] | Milestones | 100% | 10% | 10%
[7 empty] | Equipment Progress | 45% | 10% | 4.5%
[7 empty] | Handovers | 0% | 5% | 0%
[7 empty] | CONTRACT HEALTH INDEX |  |  | 56%
THE DASHBOARD ANSWERS
What is late? | 0 documents overdue, 0 actions overdue
What is missing? | 0 deliverables not started
What is blocking commissioning? | 1 open commissioning blockers
Who owns the blocker? | A. Mercer (1)
Which scopes are not ready? | 1 of 1 scopes below the ready threshold
Which equipment items are behind schedule? | 0 equipment items past planned finish
Which documents are not approved? | 1 of 1 deliverables not yet approved
Which milestones are at risk? | 0 milestones at risk or delayed
Which actions are due this week? | 1 actions due within 7 days
MILESTONE TRACKER | [7 empty] | READINESS TREND LOG
Milestone | Scope | Planned Date | Forecast Date | Actual Date | Status | Owner | Days | Snapshot Date | Contract Readiness %
Kick Off Meeting |  | 2026-06-06 |  |  |  |  | -75
Commissioning Readiness Review |  | 2027-04-02 |  |  |  |  | 225
Authority To Start |  | 2027-05-18 |  |  |  |  | 271
Commissioning Start |  | 2027-06-01 |  |  |  |  | 285
Functional Takeover |  | 2027-08-15 |  |  |  |  | 360
Beneficial Use |  | 2027-08-25 |  |  |  |  | 370
Maintenance Transfer |  | 2027-09-09 |  |  |  |  | 385
Temporary Operations Transfer |  | 2027-09-24 |  |  |  |  | 400
Final Takeover |  | 2027-10-09 |  |  |  |  | 415
REQUIRED CHARTS
Formulas:
Planned Date = IFERROR(Ctrl_PlannedStart-INDEX(Cfg_MsLeadDays,MATCH([Milestone],Cfg_MsList,0)),"")
Days = IF([Milestone]="","",IF([Status]="Achieved","",IF([Forecast Date]<>"",[Forecast Date]-TODAY(),IF([Planned Date]<>"",[Planned Date]-TODAY(),""))))
Note on J25: The workbook holds no history of its own. Record one snapshot per month: type the date and paste the Contract Readiness value from the Control Panel as a number. The Readiness Trend chart plots this table.

## Configuration (hidden)
CONFIGURATION — WORKBOOK LOGIC
Administrative sheet. Dropdown lists, progress maps, Health Index weights and RAG thresholds live here. Lead times are edited on the Control Panel. Do not delete rows or columns — every other sheet references these ranges by name.
Contract Status | Scope Status | Commissioning Phase | Workflow Status | Readiness Gate | Priority | Action Status | Criticality | Yes / No | Milestone Status | Document Type | Personnel | Action Category | Milestone Name
Not Started | Not Started | Pre-Commissioning | Not Started | Preparation | Critical | Open | Critical | Yes | Not Started | Basis of Commissioning | A. Mercer | Document | Kick Off Meeting
Preparation | Preparation | Commissioning Preparation | Draft | Readiness | High | In Progress | High | No | In Progress | Surveillance Strategy | S. Okonkwo | Technical | Commissioning Readiness Review
In Progress | Review | Documentation Review | Internal Review | Authority To Start | Medium | Waiting | Medium |  | At Risk | Surveillance Programme | L. Fontaine | Quality | Authority To Start
Commissioning | Ready | Testing Preparation | Submitted | Commissioning | Low | Closed | Low |  | Delayed | Competency Evidence | D. Petrov | Safety | Commissioning Start
Handover | In Progress | Testing In Progress | Under Review | Results |  |  |  |  | Achieved | Safe System Of Work | M. Haddad | Commercial | Functional Takeover
Complete | Complete | Results Review | Comments Received | Handover | [5 empty] | Risk Assessment And Method Statement | J. Whitfield | Resource | Beneficial Use
On Hold | On Hold | Ready For Handover | Rework | Final Takeover | [5 empty] | System Commissioning Programme | K. Rasmussen | Interface | Maintenance Transfer
|  | Beneficial Use | Resubmitted | [6 empty] | Commissioning Procedure | P. Nakamura | Client | Temporary Operations Transfer
|  | Further Testing | Approved | [6 empty] | Inspection and Test Plan | R. Bellamy |  | Final Takeover
|  | Final Handover | Released | [6 empty] | Initial End Of Erection Status Report | T. Oyelaran
|  | Complete | Implemented | [6 empty] | Planned End Of Erection Status Report | N. Bergstrom
|  |  | Closed | [6 empty] | Authority To Start Evidence | C. Vasquez
[10 empty] | Commissioning Results Sheet | H. Lindqvist
[10 empty] | Commissioning Phase Report | F. Moreau
[10 empty] | Handover Certificate | G. Ashworth
[10 empty] | Functional Takeover Package | E. Devereux
Care And Maintenance Plan
Maintenance Transfer Package
Temporary Operations Transfer Package
Final End Of Erection Status Report
PHASE PROGRESS MAP |  |  | WORKFLOW STATUS MAP |  |  |  | READINESS & TIMING PARAMETERS |  |  | CONTRACT HEALTH INDEX WEIGHTS |  |  | THRESHOLDS
Commissioning Phase | Progress % |  | Workflow Status | Progress % | Counts As Approved |  | Parameter | Value |  | Component | Weight |  | Threshold | Value
Pre-Commissioning | 0% |  | Not Started | 0% | 0 |  | Equipment readiness — phase weight | 50% |  | Documents | 40% |  | Health — Excellent (min) | 90%
Commissioning Preparation | 10% |  | Draft | 15% | 0 |  | Equipment readiness — document weight | 50% |  | Readiness | 20% |  | Health — Good (min) | 75%
Documentation Review | 20% |  | Internal Review | 30% | 0 |  | Review days (submission → approval) | 21 |  | Actions | 15% |  | Health — Attention Required (min) | 50%
Testing Preparation | 30% |  | Submitted | 45% | 0 |  |  |  |  | Milestones | 10% |  | RAG — Green (min) | 75%
Testing In Progress | 45% |  | Under Review | 55% | 0 |  | Equipment with no linked documents falls back to 100% phase weight. |  |  | Equipment Progress | 10% |  | RAG — Amber (min) | 50%
Results Review | 60% |  | Comments Received | 50% | 0 |  |  |  |  | Handovers | 5% |  | Document due-soon window (days) | 30
Ready For Handover | 70% |  | Rework | 40% | 0 |  |  |  |  | TOTAL | 100% |  | Action due-soon window (days) | 14
Beneficial Use | 80% |  | Resubmitted | 70% | 0 | [7 empty] | Scope 'Ready' threshold | 80%
Further Testing | 85% |  | Approved | 90% | 1 | [7 empty] | Upcoming milestone window (days) | 30
Final Handover | 95% |  | Released | 95% | 1
Complete | 100% |  | Implemented | 98% | 1
|  |  | Closed | 100% | 1
Assumption: the % ramp across the 11 spec phases is not defined in the source document. Edit the blue cells to retune.
ATS READINESS GATE — MINIMUM REQUIRED APPROVED DELIVERABLES
Required Document Type | Approved | Outstanding | Met (1/0)
Planned End Of Erection Status Report | 0 | 0 | 0
System Commissioning Programme | 0 | 1 | 0
Commissioning Procedure | 0 | 0 | 0
Inspection and Test Plan | 0 | 0 | 0
Surveillance Strategy | 0 | 0 | 0
Surveillance Programme | 0 | 0 | 0
Competency Evidence | 0 | 0 | 0
Safe System Of Work | 0 | 0 | 0
Risk Assessment And Method Statement | 0 | 0 | 0
Authority To Start Evidence | 0 | 0 | 0
ATS Readiness Score | 0%
ATS Status | Not Ready
Types Met | 0 of 10
CHART DATA — generated automatically, do not edit
Scope | Readiness % |  | Equipment Status | Count |  | Document Status | Count |  | Document | Days Late | key |  | Action | Days Overdue | key | Owner | Open Items | Open Blockers | Milestone | Days From Today
Traction Power & 33kV Distribution | 22.5% |  | Not Started | 0 |  | Not Started | 0 | [8 empty] | A. Mercer | 1 | 1 | Kick Off Meeting | -75
|  |  | In Progress | 1 |  | Draft | 0 | [8 empty] | S. Okonkwo | 0 | 0 | Commissioning Readiness Review | 225
|  |  | Behind Schedule | 0 |  | Internal Review | 0 | [8 empty] | L. Fontaine | 0 | 0 | Authority To Start | 271
|  |  | Complete | 0 |  | Submitted | 0 | [8 empty] | D. Petrov | 1 | 0 | Commissioning Start | 285
[6 empty] | Under Review | 1 | [8 empty] | M. Haddad | 0 | 0 | Functional Takeover | 360
[6 empty] | Comments Received | 0 | [8 empty] | J. Whitfield | 0 | 0 | Beneficial Use | 370
[6 empty] | Rework | 0 | [8 empty] | K. Rasmussen | 0 | 0 | Maintenance Transfer | 385
[6 empty] | Resubmitted | 0 | [8 empty] | P. Nakamura | 0 | 0 | Temporary Operations Transfer | 400
[6 empty] | Approved | 0 | [8 empty] | R. Bellamy | 0 | 0 | Final Takeover | 415
[6 empty] | Released | 0 | [8 empty] | T. Oyelaran | 0 | 0
[6 empty] | Implemented | 0 | [8 empty] | N. Bergstrom | 0 | 0
[6 empty] | Closed | 0 | [8 empty] | C. Vasquez | 0 | 0
[16 empty] | H. Lindqvist | 0 | 0
[16 empty] | F. Moreau | 0 | 0
[16 empty] | G. Ashworth | 0 | 0
[16 empty] | E. Devereux | 0 | 0
Note on A57: Approved ATS-required deliverables as a share of all ATS-required deliverables in the tracker.
Note on A58: Ready only when every one of the 10 required types is fully satisfied. At Risk when 80%+ of the required deliverables are approved but at least one type still has an outstanding document.
Note on D45: A required type counts as met only when at least one document of that type exists AND none of that type is still outstanding. Counting merely 'one approved somewhere' would turn the gate green while other scopes still had the deliverable open.