## 00_Dashboard
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
Commissioning Dashboard | [8 empty] | As of:
Live counts pulled from the registers. Nothing to fill in on this sheet - readiness indicators show TBC when there is not enough underlying information to judge them.
Open Topics |  |  | Topics Requiring Discussion |  |  | Open Actions |  | Overdue Actions
Actions Due Soon |  |  | Closed Actions (this month) |  |  | Commissioning Blockers |  | Escalations Required
PQCP Follow-Up Items |  |  | PQCP Items Not Ready |  |  | Evidence Missing / Outstanding
Commissioning Readiness View
Area | Topics | Blockers | Open | Readiness
Documentation
Surveillance
Handover / Completion
Configuration
Schedule / Interfaces
SSOW / Safety
Contractor / Team Capability
PQCP Follow-Up
Top 5 Commissioning Blockers
Topic | Impact | Owner | Required By | Next Step
Actions Requiring Attention (overdue or critical)
Action ID | Action | Owner | Due Date | Status | Priority
Upcoming Key Dates / Milestones
Milestone | Category | Target Date | Status | Comment
Static Completion - Example Ventilation System | Handover / Completion | 2026-08-01 | On Track | Fictional example only.
Legend: Blue = fill in yourself ¦ Black = automatic formula, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically

## 01_Next_Meeting
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
Next Meeting - Chair the Review
Every topic below is pulled in automatically because it is flagged 'Discuss at Next Meeting', has an open point, a question, an overdue action, a Commissioning Blocker, an escalation, or a PQCP follow-up requirement. Nothing to maintain here - it reads the registers live.
After the meeting: copy 'Today's Update' + 'Decision' into Update History, copy 'New Action' rows into the Action Register, and update the Topic Register's Current Position / Status / Discuss flag for anything that changed.
Meeting Date: | 2026-07-07 |  | Topics on agenda:
REFERENCE / AUTOMATIC INFORMATION | [16 empty] | MEETING INPUT - complete live, then copy into the registers afterwards
Category | Sub-category | Topic ID | Topic | Discipline | System / Scope | Current Position | Change Since Last Review | Latest Update | Outstanding Point / Gap | Question to Ask Today | Existing Action | Existing Action Owner | Due Date | Action Status | PQCP Step / Impact | Commissioning Blocker? | Today's Update | Decision | New Action | New Action Owner | New Due Date | Priority | Blocker? Yes/No | PQCP Follow-Up Required? | Next Step | Discuss at Next Meeting?

## 02_Topic_Register
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
Topic Register
The central table. Every subject tracked across Commissioning Reviews, showing the CURRENT position only - full history lives in Update History. Add a new topic by typing in the row directly below the table.
Legend: Blue = fill in yourself ¦ Black = automatic formula, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically
Identification | [6 empty] | Position |  |  |  |  | Automatic |  | Status & Ownership |  |  |  | Meeting | Commissioning Blocker |  |  |  |  | PQCP & Evidence Links | [5 empty] | Helpers
Topic ID | Category | Sub-category | Discipline | System / Scope | Commissioning Stage | ATP / Gateway | Topic | Current Position | Change Since Last Review | Outstanding Point / Gap | Question / Decision Required | Last Review Date | Latest Update | Status | Priority | Owner / Lead | Next Step | Discuss at Next Meeting? | Commissioning Blocker? | Blocker Category | Impact | Required By | Escalation Required? | Related Action ID(s) | Related PQCP Step(s) | PQCP Relevance | PQCP Follow-Up Required? | PQCP Comment / Impact | Related Evidence ID(s) | Meeting Flag | Meeting Rank
| Commissioning Documentation | Commissioning Execution Plan | Mechanical | Example Ventilation System | Pre-Commissioning | ATP2 - Pre-Commissioning | Example Ventilation System Commissioning Strategy | Draft strategy issued for internal review. | Contractor A confirmed the temporary supply date is still to be finalised. | Confirmation required regarding temporary supply availability. | Confirm expected temporary supply date. |  |  | Open | High | Person A | Await Contractor A's updated programme. | Yes | Yes | Temporary Services | Commissioning start date at risk if the temporary supply is delayed. | 2026-07-15 | No | A001 | P-001 | Yes | Yes | Temporary supply confirmation required to progress PQCP step P-001. | E001
| Safety / Capability | Safe System of Work | Multi-discipline | Example Area B | Commissioning | ATP3 - Commissioning | Safe System of Work review - Example Area B | SSOW reviewed and accepted; no outstanding points. | Action closed - SSOW accepted. |  |  |  |  | Monitoring | Low | Person B | None - monitor for any change in scope. | No | No |  |  |  | No | A002 |  | No | No |  | E002

## 03_Action_Register
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
Action Register
Every action raised at a Commissioning Review. Add a new action by typing in the row directly below the table.
Legend: Blue = fill in yourself ¦ Black = automatic formula, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically
Identification |  |  | Ownership |  | Dates & Status |  |  |  | Automatic |  |  |  | Follow-up |  |  | Links |  |  | Closure |  |  | Helpers
Action ID | Topic ID | Action Description | Owner | Organisation / Party | Date Raised | Due Date | Status | Priority | Days Open | Days to Due Date | Overdue? | Latest Update | Next Step | Commissioning Blocker? | Escalation Required? | Related PQCP Step | Related Evidence ID | Source Meeting Date | Closure Date | Closure Evidence / Reference | Closure Comment | Attention Flag | Attention Rank
| T001 | Contractor A to provide an updated programme for the Example Ventilation System temporary supply. | Person A | Contractor A | 2026-06-02 | 2026-07-15 | In Progress | High |  |  |  |  | Follow up with Contractor A if the programme is not received. | Yes | No | P-001 | E001 | 2026-06-02
| T002 | Person B to confirm the Safe System of Work review is complete for Example Area B. | Person B | Client Team | 2026-04-10 | 2026-05-01 | Closed | Medium |  |  |  |  | None - closed. | No | No |  | E002 | 2026-04-10 | 2026-04-28 | DOC-EXAMPLE-002 rev A | SSOW reviewed and accepted.
Formulas:
Automatic = IF([Topic Register]="","",IF([Closure]<>"",[Closure]-[PQCP Follow Up],TODAY()-[PQCP Follow Up]))
Days to Due Date = IF(OR([Topic Register]="",[Document Evidence]=""),"",[Document Evidence]-TODAY())
Overdue? = IF([Topic Register]="","",IF(AND([Meeting Summary]<>"Closed",[Meeting Summary]<>"Cancelled",[Document Evidence]<>"",[Document Evidence]<TODAY()),"Yes","No"))

## 04_Update_History
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
Update History
One row per update given at a review. This is the permanent record - Topic and Action Registers only ever show the CURRENT position, pulled from here automatically.
Legend: Blue = fill in yourself ¦ Black = automatic formula, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically
Identification |  |  |  | Content |  | Status Trail |  |  |  | Admin
Update ID | Meeting Date | Topic ID | Action ID | Update / Discussion | Decision | Previous Topic Status | New Topic Status | Previous Action Status | New Action Status | Updated By | Source / Comment
| 2026-06-02 | T001 | A001 | Contractor A confirmed the temporary supply date is still to be finalised; the draft strategy remains under internal review. |  | Monitoring | Open |  | In Progress | Person A | Monthly Commissioning Review
| 2026-04-10 | T002 | A002 | Person B confirmed the Safe System of Work review is complete for Example Area B. | SSOW accepted; action closed. | Open | Monitoring | In Progress | Closed | Person B | Monthly Commissioning Review

## 05_PQCP_Follow_Up
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
PQCP Follow-Up
This is NOT the official PQCP - the official PQCP stays in its own separate worksheet/file and is the source of truth. This table only tracks the operational follow-up (discussion, evidence, action) needed for specific PQCP steps.
Reminder: the official PQCP is a separate worksheet/file and remains the source of truth for formal readiness/compliance. This table is only an operational tracker.
Legend: Blue = fill in yourself ¦ Black = automatic formula, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically
Identification |  |  | Position |  |  |  |  | Links & Ownership |  |  |  |  | Follow-up
PQCP Step | Short Subject | Category | Current Position | Gap / Information Required | Evidence Required | Evidence Available? | Evidence Reference | Related Topic ID | Related Action ID | Owner | Target Date | Last Discussed | Next Step | Discuss at Next Meeting? | Readiness Assessment | Readiness Indicator | Comment
P-001 | Temporary supply availability | Schedule & Interfaces | Awaiting contractor confirmation of the temporary supply date. | Temporary supply date not yet confirmed. | Updated programme confirming the supply date. | No | E001 | T001 | A001 | Person A | 2026-07-15 | 2026-06-02 | Await Contractor A's updated programme. | Yes | Not Ready |  | Fictional example only.
P-002 | SSOW acceptance - Example Area B | Safety / Capability | SSOW reviewed and accepted. |  | Approved SSOW document. | Yes | E002 | T002 | A002 | Person B | 2026-04-25 | 2026-04-10 | None - closed. | No | Ready |  | Fictional example only.

## 06_Document_Evidence
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
Document / Evidence Register
Documents and records supporting Commissioning readiness, topic closure, action closure or PQCP follow-up. Not a full document management system - only what this Review needs to track.
Legend: Blue = fill in yourself ¦ Black = automatic formula, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically
Identification |  |  |  |  | Status |  |  |  | Links |  |  | Tracking
Evidence ID | Document Type | Short Description | Document Reference | Revision | Status | Available? | Approved / Accepted? | Responsible Party | Related Topic ID | Related Action ID | Related PQCP Step | Required By | Latest Status / Comment | Last Checked
| Method Statement | Temporary supply installation method statement - Example Ventilation System | DOC-EXAMPLE-001 | A | Draft | No | TBC | Contractor A | T001 | A001 | P-001 | 2026-07-10 | Awaiting contractor issue. | 2026-06-02
| Safe System of Work | SSOW for Example Area B | DOC-EXAMPLE-002 | A | Approved | Yes | Yes | Client Team | T002 | A002 |  | 2026-04-25 | Reviewed and accepted. | 2026-04-28

## 07_Meeting_Summary
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
Meeting Summary
Fill in the meeting information and Executive Summary manually. Every section below fills in automatically from the registers for the meeting date selected - nothing else to maintain here.
Meeting Date: | 2026-06-02 |  | Meeting Title: | Monthly Commissioning Review - Example Project
Prepared By: | Person A |  | Participants / Attendees: | Person A, Person B, Contractor A representative
EXECUTIVE SUMMARY (max 5 points)
1. | Fictional example: temporary supply confirmation remains the key open item for Example Ventilation System.
2.
3.
4.
5.
KEY UPDATES
Topic ID | Update | Current Position
DECISIONS
Topic ID | Decision
NEW ACTIONS
Action | Owner | Due Date | Priority
CLOSED ACTIONS
Action | Owner | Closure Evidence | Closure Date
PQCP / READINESS FOLLOW-UP
PQCP Step | Current Position | Gap | Next Step
KEY COMMISSIONING BLOCKERS
Topic | Impact | Owner | Required By | Escalation
ITEMS FOR NEXT REVIEW
Topic | Outstanding Point | Next Step | Owner
Legend: Blue = fill in yourself ¦ Black = automatic formula, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically

## 08_Lists_Config
Dashboard | Next Meeting | Topic Register | Action Register | Update History | PQCP Follow Up | Document Evidence | Meeting Summary
Lists & Configuration
Every dropdown list used across the workbook. Edit these lists to match your project's vocabulary - changes here update every dropdown automatically.
Category | Sub-category | Discipline | Commissioning Stage | ATP / Gateway | Topic Status | Action Status | Priority | Yes/No | Yes/No/TBC | Readiness Assessment | Evidence Availability | Evidence Status | Document Type | Blocker Category | Organisation / Party | Approved? | Milestone Status
Commissioning Documentation | Commissioning Execution Plan | Mechanical | Design | ATP1 - Static Completion | Open | Open | Low | Yes | Yes | Ready | Yes | Draft | Commissioning Execution Plan | Documentation | Contractor A | Yes | Not Started
Reviews & Surveillance | Commissioning Programme / SCP | Electrical | Construction | ATP2 - Pre-Commissioning | Monitoring | In Progress | Medium | No | No | Partially Ready | No | Issued for Review | Commissioning Programme / SCP | Design | Contractor B | No | On Track
Handover / Completion | Commissioning Procedures | I&C / Controls | Static Completion | ATP3 - Commissioning | Awaiting Information | Awaiting Information | High |  | TBC | Not Ready | Partial | Approved | Commissioning Procedure | Schedule | Client Team | N/A | At Risk
Configuration | Method Statements | Civil / Structural | Pre-Commissioning | ATP4 - Integrated Commissioning | In Progress | Awaiting Contractor | Critical |  |  | N/A | TBC | Superseded | Method Statement | Interface | Other | TBC | Complete
Schedule & Interfaces | Inspection & Test Plans | Process | Commissioning | N/A | Open: On Hold; Open: Awaiting Client; Draft: Missing | Inspection & Test Plan | Temporary Services |  |  | Missed
Safety / Capability | Commissioning Result Sheets / Test Results | HVAC | Integrated Commissioning | Other | Open: Closed; Open: Awaiting Internal Team; Draft: TBC | Commissioning Result Sheet / Test Record | Permanent Services
Commissioning Control | LOD / LDRC | Telecoms | Handover |  | Open: On Hold | EESR / Completion Evidence | Safety / SSOW
Quality | Commissioning Completion Report | Multi-discipline | Final Completion |  | Open: Closed | Handover Evidence | Resources / Competence
Other | Surveillance Strategy | Other | N/A |  | Open: Cancelled | Safe System of Work | Surveillance
| Surveillance Programme |  | Other | [9 empty] | RAMS | Handover
| Witness Points | [11 empty] | Surveillance Strategy | Configuration
| Hold Points | [11 empty] | Surveillance Record | Quality
| Inspection / Surveillance Notifications | [11 empty] | O&M Documentation | Contractual / Scope
| SONIMS or equivalent | [11 empty] | Configuration Record | Other
| Supporting Surveillance Documentation | [11 empty] | Training / Competence Evidence
| Partitioning Strategy | [11 empty] | Commissioning Completion Report
| Planned Erection / Completion Status | [11 empty] | Other
Final Erection / Completion Status
Handover
Care & Maintenance
O&M Documentation
Outstanding Works / Open Points
Configuration Baseline
System / Asset Coding
Temporary Means / Devices
Design Configuration
Final Configuration
Configuration Records
Commissioning Programme
Commissioning Start Date
Commissioning Sequence
Static Completion
Pre-Commissioning
Integrated Commissioning
Temporary Services
Permanent Services
Integrated Schedule
Contract Interfaces
Scope Gaps
External Dependencies
Safe System of Work
Mechanical SSOW
Electrical SSOW
RAMS
Training
Competence
SQEP
Commissioning Team Readiness
NCR / Non-Conformance
Deviations
Change Management
Retesting
Authority to Start Commissioning
Commissioning Control Point
Gateway Readiness
Document Review
Acceptance
Quality Records
LTQR
Audit
Closeout
Other
Configuration Parameters
Parameter | Value
'Due soon' warning window (calendar days before due date) | 14
Legend: Blue = fill in yourself ¦ Black = automatic formula, do not overtype ¦ Grey columns = automation helpers, leave untouched ¦ New row: type directly below the table and Excel extends it automatically