## 00_Dashboard
Commissioning Dashboard | [8 empty] | As of:
Live counts pulled from the Topic, Action and PQCP registers. Nothing to fill in on this sheet.
Open Topics |  |  | Open Actions |  |  | Overdue Actions | Actions Due Soon | Closed Actions
PQCP Completion % |  |  | PQCP Items Complete |  |  | PQCP Items In Progress | PQCP Missing Evidence | PQCP Not Started
Overall Readiness
Top 5 Blockers / Critical Open Items
Action ID | Action | Owner | Due Date | Status | Priority
Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit

## 01_Next_Meeting
Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit
Chair the meeting directly from this sheet. Rows below fill in automatically for every topic flagged 'Discuss at Next Meeting = Yes', with an overdue action, or with an open question - nothing to maintain here.
Meeting Date: | 2026-08-05 |  | Topics on agenda:
Topic ID | Topic | Current Position | Latest Update | Open Point / Question | Action | Owner | Due Date | Input / Decision Required

## 02_Topic_Register
Topic Register |  |  |  |  | Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit
Topic ID | Category | Sub-category | Topic | Current Position | Outstanding Point / Question | Status | Priority | Owner | Last Update | Next Step | Discuss at Next Meeting? | Related Action ID | Related PQCP Requirement | Related Document / Evidence | Flag | Rank
| Systems & Equipment | Pump Skid A | Pump skid A commissioning sequence | Functional test completed; awaiting punch list closure. | Punch list item #4 (instrumentation calibration) still open. | Open | High | J. Smith |  | Confirm calibration certificate received. | Yes | A001 | P001 | E001
| Documentation | ITP Register | Inspection & Test Plan sign-off backlog | 6 of 10 ITPs signed off by the contractor. | 4 ITPs pending contractor signature. | Monitoring | Medium | A. Diallo |  | Escalate to contractor PM if no response. | No | A002 | P002 | E002
| Interfaces | Electrical / Mechanical | Interface clearance for Skid B power feed | Interface closed - confirmed by both parties. |  | Closed | Low | M. Chen |  | None - closed. | No | A003 |  | E002

## 03_Action_Register
Action Register | [5 empty] | Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit
Action ID | Topic ID | Action | Owner | Organisation | Date Raised | Due Date | Status | Priority | Days Open | Overdue | Latest Update | Next Step | Closure Date | Closure Evidence | Source Meeting Date | Flag | Rank
| T001 | Chase contractor for instrumentation calibration certificate (Punch item #4) | J. Smith | Acme Mechanical Ltd | 2026-07-03 | 2026-08-15 | In Progress | High |  |  | Certificate requested, contractor to issue by end of week. | Follow up if not received by due date |  |  | 2026-07-03
| T002 | Escalate outstanding ITP sign-offs to contractor project manager | A. Diallo | Northwind Engineering | 2026-06-05 | 2026-07-01 | Awaiting Contractor | Medium |  |  | Escalation email sent, awaiting contractor response. | Re-escalate if no response in 5 days |  |  | 2026-06-05
| T003 | Confirm interface clearance sign-off filed in document register | M. Chen | Acme Mechanical Ltd | 2026-05-02 | 2026-05-20 | Closed | Low |  |  | Sign-off confirmed and filed. | None - closed | 2026-05-18 | E002 - Interface Clearance Record rev B | 2026-05-02
Formulas:
Days Open = IF([Topic ID]="","",IF([Closure Date]<>"",[Closure Date]-[Date Raised],TODAY()-[Date Raised]))
Overdue = IF(OR([Topic ID]="",[Status]="Closed",[Due Date]=""),"No",IF([Due Date]<TODAY(),"Yes","No"))

## 04_Update_History
Update History |  |  |  | Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit
Update ID | Meeting Date | Topic ID | Action ID | Update | Decision | Previous Status | New Status | Updated By
| 2026-07-03 | T001 | A001 | Functional test complete. One punch item remains (instrumentation calibration). |  | Monitoring | Open | J. Smith
| 2026-06-05 | T002 | A002 | 6 of 10 ITPs signed off; contractor slow to close remaining 4. | Agreed to formally escalate to contractor PM. | Open | Monitoring | A. Diallo
| 2026-05-02 | T003 | A003 | Interface clearance confirmed by both mechanical and electrical leads. | Topic closed. | Open | Closed | M. Chen

## 05_PQCP_Tracker
PQCP / Readiness Tracker |  |  |  |  | Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit
PQCP ID | Section / Step | Requirement | Verification Question | Required Evidence | Responsible Person | Status | Readiness % | Evidence Available? | Evidence Reference | Evidence Status | Gap / Outstanding Item | Target Date | Related Topic ID | Related Action ID | Last Review Date | Next Step
| Mechanical Completion - Pump Skid A | Instrumentation calibrated and certified prior to functional test | Is the calibration certificate available and approved? | Calibration certificate | J. Smith | Information Required | 70% | Partial | E003 |  | Calibration certificate not yet issued by contractor. | 2026-08-15 | T001 | A001 | 2026-07-03 | Review once certificate received.
| Documentation Closeout | All ITPs formally signed off by the contractor | Are all ITPs signed and filed? | Signed ITP register | A. Diallo | In Progress | 60% | Partial | E001 |  | 4 of 10 ITPs still unsigned. | 2026-07-20 | T002 | A002 | 2026-06-05 | Escalate outstanding ITPs.
| Interface Management | Electrical / mechanical interface formally closed with sign-off from both parties | Is the interface clearance record approved and filed? | Interface clearance record | M. Chen | Complete | 100% | Yes | E002 |  |  | 2026-05-20 | T003 | A003 | 2026-05-18 | None - closed.

## 06_Document_Evidence
Document / Evidence Register |  |  |  | Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit
Evidence ID | Document Type | Description | Document Reference | Revision | Status | Related PQCP ID | Related Topic ID | Required Date | Available? | Approved? | Comments
| Inspection & Test Plan | ITP for Pump Skid A instrumentation | ITP-PSA-001 | B | Approved | P001 | T001 | 2026-07-10 | Yes | Yes | Filed in document register.
| Handover / Erection Completion Evidence | Interface clearance record - Skid B power feed | ECR-SKB-014 | A | Approved |  | T003 | 2026-05-15 | Yes | Yes
| Commissioning Result Sheet | Functional test result sheet - Pump Skid A | CRS-PSA-002 | - | Draft | P001 | T001 | 2026-08-01 | No | No | Awaiting calibration certificate before final issue.

## 07_Meeting_Summary
Meeting Summary
Pick a meeting date below - every section fills in automatically from the registers, ready to paste into minutes or an email. Record the actual discussion directly in the Topic Register, Action Register and Update History; this sheet only compiles what you logged there.
Meeting Date: | 2026-06-05
KEY UPDATES
Topic ID | Update
DECISIONS
Topic ID | Decision
NEW ACTIONS
Action | Owner | Due Date
CLOSED ACTIONS
Action | Owner | Closure Evidence
POINTS FOR NEXT MEETING
Topic | Next Step
Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit

## 08_Lists_Config
Lists & Configuration
Dropdown lists and parameters used across the workbook. Edit the lists below to match your project's vocabulary.
Category | Topic Status | Priority | Yes/No | Action Status | PQCP Status | Evidence Available | Document Type | Document Status | Approved?
Schedule | Open | Low | Yes | Open | Not Started | Yes | Commissioning Execution Plan | Draft | Yes
Documentation | Monitoring | Medium | No | In Progress | Information Required | No | Commissioning Programme | Issued for Review | No
Systems & Equipment | Closed | High |  | Awaiting Information | In Progress | Partial | Commissioning Procedure | Approved | N/A
Interfaces |  | Critical |  | Awaiting Contractor | Under Review |  | Method Statement | Superseded
Resources |  |  |  | Awaiting Client | Evidence Available |  | Inspection & Test Plan | Missing
Quality |  |  |  | On Hold | Complete |  | Commissioning Result Sheet
HSE |  |  |  | Closed | N/A |  | Handover / Erection Completion Evidence
Contract | [6 empty] | Safe System of Work
Readiness / PQCP | [6 empty] | Surveillance Evidence
Other | [6 empty] | O&M Documentation
Commissioning Completion Report
Configuration Parameters
Parameter | Value
'Due soon' warning window (days before due date) | 14
Legend: Blue text = fill in yourself ¦ Black text = automatic formula, do not overtype ¦ Grey columns = automation helpers, do not edit