## Overview
DMIC Contract Overview | [7 empty] | As of
Live rollup across all contracts - pulled from Contracts, Schedule & Status and Risk & Phase.
Systems by contract
[12 empty] | Choose a contract: | UK-EX01
Total contracts |  | Average risk |  | Critical (risk ≥ 60%) |  | Watch (30–59%)
Contract Number | Area | Contractor | Description | Current Phase | Total Risk % | Next Milestone | Days to Milestone | Commissioning Engineer | Commissioning Manager | DMIC Co-ordinator | Status
Formulas:
Days to Milestone = IF(OR([Total contracts]="",[Watch (30–59%)]=""),"",[Watch (30–59%)]-TODAY())

## DMIC List - master
Contracts
Single source of truth — contract identity and key personnel. Every other tab looks this up, never retypes it.
Contract Information | [7 empty] | Key Personnel | [10 empty] | Notes
Contract Number | Area | Contractor | Description | Programme | Contract Type | Contract Form | Contractor Commissioning Level | Delivery Manager | Senior Project Manager | PM / APM | Commercial Lead | Commercial Manager | Commissioning Engineer | Commissioning Manager | Quality Management Lead | Contractor Project Director / Manager | Contractor Construction / Site Manager | DMIC Co-ordinator | Notes
UK-EX01 | Nuclear Island | REEL (formerly NFM) | Airlocks | FH&L | FIDIC - DMIC | Two-Stage | Full | David Munro | Keith Nailard | James Fayemiwo | John Gallagher | John Gallagher | Adrian Kraemer | Feng Liu | Priya Anand | Kevin McDevitt | Leigh Yule | Sofia Marchetti
UK-EX02 | Conventional Island and BOP | APCO | Polar Crane | FH&L | FIDIC - DMIC | Single-Stage | Partial | David Munro | Keith Nailard | Simon Stacey | John Gallagher | Richard Brown | Richard Brown | Leigh Yule | Priya Anand | Kevin McDevitt | Leigh Yule | Sofia Marchetti
UK-EX03 | Site Wide / I&C | Balfour Beatty | Control Systems Integration | I&C | NEC4 | Two-Stage | Support Only | David Munro | Keith Nailard | Stuart Cameron | John Gallagher | Gustavo Aguilar | Samuel Everett | Leigh Yule | Priya Anand | Kevin McDevitt | Leigh Yule | Sofia Marchetti

## Commissioning Readiness
Schedule & Status | [10 empty] | Today's Date:
Contract Number, contractor and key personnel are live look-ups from Contracts — never retyped here.
Contract Information |  |  |  | Key Personnel |  |  | Schedule | [6 empty] | DMIC Kick-off |  | Commissioning Contract Status |  |  | Software
Contract Number | Area | Contractor | Description | Commissioning Engineer | Commissioning Manager | DMIC Co-ordinator | First Date - as per P6 Schedule | Date Changes (editable) | Driver / Comment | Next Phase Date (if in flight) | Driver | T - X Months | Schedule in P6 | T-18 Kick-off Meeting Date (Incl. PM & Comm.) | T-12 Kick-off Meeting Date (Contractor) | Appendix 4 Revision CBL100100449 | Appendix 4 - contract specific | Appendix 4 Comments | NCRs on Switch | FCRs on Switch | Sonims | Open Points | TMDs | Standards & Expectations Day | Applicable System Codes
[7 empty] | 2027-03-01 |  |  | 2027-04-15 | Next Phase kick-off |  |  | 2025-10-14 | 2026-04-15
[7 empty] | 2026-11-01 |  |  | 2026-10-02 | T-12 kick-off overdue |  |  | 2025-04-02 | 2025-10-02
[7 empty] | 2027-09-01 |  |  | 2026-09-30 | Standards & Expectations Day booked |  |  | 2025-03-31 | 2025-09-30

## DMIC DMS Commissioning-master
Risk & Phase
Contract identity is a live look-up from Contracts. Total Risk % is calculated from the 4 risk scores.
Contract Information |  |  |  | Key Personnel |  |  | Capability & Complexity |  | Phase |  | Risk relating to: | [5 empty] | Appendix / Systems
Contract Number | Area | Contractor | Description | Commissioning Engineer | Commissioning Manager | DMIC Co-ordinator | Contractor Capability Rating (10 = highest capability) | Contract Complexity Rating (10 = most simple) | Commissioning Start Date | Current Phase of Contract | Schedule Risk | Documentation Risk | Integration / Collaboration Risk | Team / Resource Risk | Total Risk Percentage | Risk Commentary | Appendix 4 Revision | Commentary | Systems
[9 empty] | 2027-03-01 | Commissioning Preparation | 2 | 1 | 2 | 1
[9 empty] | 2026-11-01 | Commissioning | 4 | 3 | 4 | 3
[9 empty] | 2027-09-01 | Design | 1 | 1 | 1 | 1

## Competency&Complexity
Competency & Complexity
Contract identity is a live look-up from Contracts. Score combines the capability and complexity ratings below.
Contract Information |  |  |  | Key Personnel |  |  | Contractor Capability | [5 empty] | Scope Complexity |  |  |  |  | NNB Integration
Contract Number | Area | Contractor | Description | Commissioning Engineer | Commissioning Manager | DMIC Co-ordinator | Tier 1 Capability | Quality of Site Documents | Installation Capability | Commissioning Capability | Ability to Meet HPC Safety Requirements | Previous EPR Experience | Technical Complexity | Complexity of Interfaces | Coordination with Others | Level of NNB Surveillance | Impact on other Systems and Works | Score | Need for Integrated Team Approach | DMIC PM | NNB PM | NNB Construction Lead | NNB Commissioning Lead | NNB Technical Lead | NNB QML
[7 empty] | High | Medium | High | Medium | Medium | High | Medium | Low | Medium | Medium | Low |  |  | 1 | 1 | 0 | 0 | 0 | 0
[7 empty] | Medium | Low | Medium | Low | Low | Medium | High | High | Medium | High | Medium |  |  | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | High | High | High | High | Medium | High | Low | Low | Low | Medium | Low |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Useful Docs
Useful Docs
Contract Number, Area, contractor and key personnel are live look-ups from Contracts — never retyped here.
Contract Information |  |  |  | Key Personnel |  |  | Useful Documents | [5 empty] | Notes
Contract Number | Area | Contractor | Description | Commissioning Engineer | Commissioning Manager | DMIC Co-ordinator | Team Centre Contract | Commissioning Surveillance Strategy Doc. No. | NNB PQCP | Partitioning Strategy | DMIC Folder | Commissioning Sharepoint (Delivery) | Notes

## Site Services
Site Services
Common building logistics and who is responsible - not contract-specific.
Common Building Logistics | Employer/Contractor Obligation | Service Provider | Service Available | Responsible Party for Costs | Notes | NNB Responsible Team | How this is arranged - details
Task Lighting | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Work Area Cleaning | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Task Fire Protection/Suppression | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Temporary Power Supplies | Employer | Dalkia | Dalkia Contract xx | Employer |  |  | Area team to provide, reach out and ask 16wks out but doent always happen
Temporary Lighting | Employer | Dalkia | Dalkia Contract xx | Employer
Temporary HVAC/Heating | Employer | Dalkia | Dalkia Contract xx | Employer
General Area Cleaning | Employer | Wilson James | WJ Contract xx | Employer
Temporary Doors/Opening Protection | Employer | BYLOR/MEH | BYLOR/MEH | Employer | Confirm provider?
Internal Flow Management (signage, barriers) | Employer | Wilson James | WJ Contract xx | Employer |  |  | FAYAT responsible for barriers they have their own
External Flow Management (signage, barriers) | Employer | Wilson James | WJ Contract xx | Employer
Temporary Fire Stops | Employer | Wilson James | WJ Contract xx | Employer
Temporary Fire Detection | Employer | Wilson James | WJ Contract xx | Employer
Building Fire Points and Extinguishers | Employer | Wilson James | WJ Contract xx | Employer
Access and Lifting | Employer/Contractor Obligation | Service Provider | Service Available | Responsible Party for Costs | Notes | NNB Responsible Team | How this is arranged - details
Scaffolding | Employer | MEH / DMIC Contactor | MEH "Access for Others" | Employer | Direct hire of scaffolding by certain DMIC Contractors (e.g. H&E, Otis,…) |  | Fyat contracts exclude scaffolding. Go out with scaffolders walk down with authorisation, Altrad.
MEWPs | Employer | DMIC Contractor | Direct hire by DMIC Contractor | Employer | NNB do not have a direct hire Contract. Proposal for DMIC Contractor to direct hire to avoid multiple fee mark-ups. |  | Sometimes availaility to share, 'exhange note' otherwise FAYAT hire in their own
Hoists and Operators | Employer | MEH | MEH | Employer | Use of hoist issue issues in HD buildings. Equans have a rigging team by are not authorised to use hoist and are dependent on MEH. Potential claims.
Cranes and Operators | Employer | BYLOR / MEH | BYLOR / MEH "Lifing for Others" | Employer | Tower cranes and mobile cranes. There is an agreed schedule of lifts for HLC. |  | TC controlled by bylor FAYAT request directly with Different areas do different things.
Construction Utilities | Employer/Contractor Obligation | Service Provider | Service Available | Responsible Party for Costs | Notes | NNB Responsible Team | How this is arranged - details
DEMIN Water | Employer | ?? | ?? | Employer | Provider to be confirmed. Availability from BOP DEMIN water plant?
Potable Water | Employer | NNB Site Ops | NNB Site Ops | Employer | Check?
Welding Gas | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Compressed/dry air | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Nitrogen / other gases | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Diesel Fuel | DMIC Contractor | NNB Site Ops | Ceretas Contract xx | DMIC Contractor | Task order to be set up. Costs backcharged to DMIC Contractors. Check with SPM/PM
Oils & Lubriucants | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Site Services | Employer/Contractor Obligation | Service Provider | Service Available | Responsible Party for Costs | Notes | NNB Responsible Team | How this is arranged - details
Office Accommodation | Employer | NNB Site Ops | NNB Site Ops | Employer | Site welfare buildings. Limited facilities provided in Contractor compound areas
Lockers and Changing Room Facilities | Employer | NNB Site Ops | NNB Site Ops | Employer | Site welfare buildings. Limited facilities provided in Contractor compound areas
Canteen Facilities | Employer | Employer | Somerset Larder | Employer
Site Security | Employer | NNB Site Ops | G4S Contract | Employer
Pest Control | Employer | NNB Site Ops | NNB Site Ops | Employer
Radios | Employer | NNB Site Ops | NNB Site Ops | Employer
Facilities Management | Employer / DMIC Contractor | NNB Site Ops | NNB Site Ops | Employer | Site welfare buildings by Employer. DOR established for contractor compound.
Waste/Effluent Removal | DMIC Contractor | Biffa | Biffa Contract xxxx | DMIC Contractor | Task order to be set up. Costs backcharged to DMIC Contractor.
PPE | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Radiographic Services | DMIC Contractor | Bilfinger | Bilfinger Contract xxxx | DMIC Contractor | Task order to be set up. Costs backcharged to DMIC Contractor.
Hydrostatic Testing | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor | Check provision of water by Employer?
Electrical Testing | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Site Surveying | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Workshop Facilities | Employer | NNB Site Ops | NNB Site Ops | Employer
Installation Tools and Equipment | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Calibration of Tools and Equipment | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Construction Consumables | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Equipment & Material Handling | Employer/Contractor Obligation | Service Provider | Service Available | Responsible Party for Costs | Notes | NNB Responsible Team | How this is arranged - details
Transportation to Warehouse | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor |  |  | FAYAT ship from france to Warehouse in UK (Wincanton) then call offs FAYAT Manage themselves
Offloading at Warehouse | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Warehouse / Storage Area | Employer | NNB Site Ops | NNB Site Ops | Employer |  |  | FAYAT Yards allocated by NNB siteops
Radiographic Storage | Employer | NNB Site Ops | TBC | Employer | Location and facility to be confirmed
Transportation AIL from warehouse to HPC | Employer | NNB Site Ops | Osprey Contract xxxx | Employer
Transportation non-AIL from warehouse to HPC | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Offloading at HPC Site | DMIC Contractor / Employer | DMIC Contractor / BYLOR / MEH | DMIC Contractor / BYLOR / MEH | DMIC Contractor / Employer | Offload by crane is by Employer
HPC onsite Outdoor Laydown Area | Employer | NNB Site Ops | NNB Site Ops | Employer
HPC onsite Indoor Warehouse | Employer | NNB Site Ops | NNB Site Ops | Employer
Movement to Point of Installation | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor
Care & Maintenance | DMIC Contractor | DMIC Contractor | DMIC Contractor | DMIC Contractor | In warehouse and when installed at HPC.

## Systems
Systems
Per-system detail (several systems per contract) - restored from the source file's "Sheet2", not linked to any other tab there either.
Contract Number | System | Suffix | System Description | Start of First Commissioning Date | BOC | Nuclear Graded?
UK-EX01 | AL-101 |  | Airlock Control System | 2027-05-01 | BOC-01 | Yes
UK-EX01 | AL-102 |  | Airlock Door Interlocks | 2027-05-15 | BOC-01 | Yes
UK-EX02 | PC-204 |  | Polar Crane Hoist & Trolley | 2026-12-01 | BOC-02 | No
UK-EX03 | CS-310 |  | Control Systems Integration Bus | 2027-10-01 | BOC-03 | Yes
UK-EX03 | CS-311 |  | Control Systems Field Network | 2027-10-15 | BOC-03 | Yes